## Control
Mini Rally - DevInt Business E2E Control
Execution summary | Count | Execution boundary
Total steps | 14 | UI and business behavior only. Test through the signed-in DevInt UI. Latest explicit BA decisions override stale SRS text and must be logged as documentation gaps. Controlled records use prefix BA-E2E-20260720 and remain for BA inspection.
Passed | 3
Failed | 6
Blocked | 3
Not Testable | 2
In Progress | 0
Not Started | 0
Logged gaps | 24

## E2E Steps
Business E2E Steps - DevInt vs BA Baseline
Step ID | Seq | Phase | Business Object | Action | Expected Business Result | SRS / Decision Reference | DevInt Route | Execution Status | BA Confirmation | Test Data ID | Actual Result | Gap IDs | Evidence | Last Tested
E2E-00 | 0 | Preflight | Context | Confirm signed-in Workspace/Project/Team context | Authorized context is visible and stable for all created records | Phase 0 Workspace + latest BA scope | App shell | Not Testable | Confirmed | CTX-01 | Signed in as Hieu Vu Minh Bui; context ACME Corp / NXP / All Teams. BA directed use of No team because Team data is not currently testable. | DEV-003 | evidence/E2E-01/02-team-not-linked.png | 2026-07-20
E2E-01 | 1 | Phase 2 | Iteration | Create one controlled Iteration | Exactly one Iteration is created with default Planning and valid dates/context | Reconciliation C04 + P2 Iterations | /timeboxes | Passed | Confirmed | IT-01 | Created IT-5 once with No team, dates 2026-07-21..2026-08-03 and default Planning; record persisted after reload. Planning/Committed/Accepted matches the confirmed reconciliation lifecycle. | DEV-002; DEV-003 | evidence/E2E-01/03-create-no-team.png; evidence/E2E-01/04-created-persisted.png | 2026-07-20
E2E-02 | 2 | Phase 3 | Release | Create two controlled Releases | Each Release is Project-level; status catalog is Planning/Active/Accepted | P3 Release FR-001..015 + reconciliation C01/C07 | Timeboxes > Releases | Passed | Confirmed | REL-01; REL-02 | Release A and B were created once, defaulted Planning, retained dates after reload, and exposed exactly Planning/Active/Accepted. BA confirmed relocation to Timeboxes and Phase 5 ownership of Progress. | DEV-004; DEV-005 | evidence/E2E-02/01-release-a-form.png; evidence/E2E-02/02-release-b-form.png; evidence/E2E-02/03-releases-persisted.png | 2026-07-20
E2E-03 | 3 | Phase 3 | Milestone | Create one controlled Milestone and link both Releases | Milestone status catalog matches; target dates derive from earliest Release start and latest Release end | P3 Milestones FR-001..013 + reconciliation C01 | Timeboxes > Milestones | Blocked | Confirmed | MS-01 | Standalone Milestone was created once with Planned and blank derived dates. Create/Edit both show No releases available, so Release linkage and expected 2026-07-20..2026-08-31 derivation cannot be executed. BA confirmed the gap and fix direction. | DEV-006 | evidence/E2E-03/01-form-no-releases.png; evidence/E2E-03/02-milestone-persisted.png; evidence/E2E-03/03-edit-no-releases.png | 2026-07-20
E2E-04 | 4 | Phase 1 | Story/Defect | Create one Story from Backlog | Exactly one Story is created; Schedule and Flow default Idea and mirror | P1 Work Item Create FR-001..013 + confirmed reconciliation C02 | /backlog | Blocked | Confirmed | WI-01 | Create failed twice. No team returns a generic unexpected error (ref c13cf2d5-6ac5-4a87-aac2-5959c1a55fd2); Team Alpha returns Team is not linked to this project. Exact-title search confirms no record. BA directed DEV-007/008 to Dev and reconfirmed DEV-009 against the Dev testing align business baseline. | DEV-007; DEV-008; DEV-009 | evidence/E2E-04/01-create-form.png; evidence/E2E-04/02-no-team-unexpected-error.png; evidence/E2E-04/03-team-not-linked.png; evidence/E2E-04/04-no-record-after-attempts.png | 2026-07-20
E2E-05 | 5 | Phase 2 | Assignment | Assign an existing Story to controlled Iteration | Assignment persists; same Work Item can be checked in Iteration Status when a valid Team context exists; Iteration remains Planning | P2 Iterations lifecycle + BA decision: no All Teams requirement | /backlog; /iteration-status | Not Testable | Confirmed | WI-01 / US-12 -> IT-01 | US-12 was assigned inline to IT-5 and persisted after Backlog reload; IT-5 remained Planning. BA confirmed Iteration Status does not need All Teams support. Cross-screen display is deferred because IT-5 has No team and Team behavior is currently Not Testable. | DEV-010 | evidence/E2E-05/01-us12-before-assignment.png; evidence/E2E-05/02-us12-assigned-inline.png; evidence/E2E-05/03-us12-assignment-persisted.png; evidence/E2E-05/04-iteration-status-no-iterations.png; evidence/E2E-05/05-team-alpha-iteration-status.png | 2026-07-20
E2E-06 | 6 | Phase 3 | Release/Milestone Assignment | Assign Story to one active Release and multiple eligible Milestones | Release is single-select; Milestones are multi-select; relations persist independently and selected Milestones survive Release changes | Reconciliation C01 + P3 Release/Milestone SRS | Work Item Detail; Backlog | Blocked | Confirmed | WI-01 / US-12 -> REL-02; planned MS-01 | US-12 accepted Release A, then Release B replaced A and persisted after reload; Backlog mirrored Release B and retained IT-5. Work Item Detail has no Milestone field. BA confirmed DEV-011 as a Dev change. | DEV-011 | evidence/E2E-06/01-us12-detail-mismatch.png; evidence/E2E-06/02-us12-release-a.png; evidence/E2E-06/03-us12-release-b-replaces-a.png; evidence/E2E-06/04-us12-release-b-persisted-no-milestone.png; evidence/E2E-06/05-us12-release-b-backlog-mirror.png | 2026-07-20
E2E-07 | 7 | Phase 1 | Task | Create two Tasks under the Story | Tasks create exactly once, inherit parent context, default Defined, update the tab count and never appear as Backlog rows | P1 Task Management + latest BA rules | Work Item Detail > Tasks | Failed | Confirmed | TA-01; TA-02 | TA-8 and TA-9 were created once under US-12, defaulted Defined, showed Project NXP / no Team, persisted after reload, and did not appear in Backlog. Totals Estimate became 6h and Detail roll-up became 6/0/0, but the tab remained 0 Tasks. Create Task still accepts editable Estimate with no To Do/Actuals, and Task rows expose no inline edit controls. BA confirmed DEV-012/013/014 for Dev correction. | DEV-012; DEV-013; DEV-014 | evidence/E2E-07/01-empty-task-dashboard.png; evidence/E2E-07/02-add-task-form.png; evidence/E2E-07/03-task-a-created.png; evidence/E2E-07/04-task-b-created-count-mismatch.png; evidence/E2E-07/05-tasks-persisted-after-reload.png; evidence/E2E-07/06-tasks-not-in-backlog.png | 2026-07-20
E2E-08 | 8 | Phase 1 | Task Time | Set To Do and Actuals | Estimate is read-only To Do + Actuals; row and Totals recalculate immediately | Latest BA decision; P1 Time SRS requires reconciliation | Task Dashboard/Detail | Failed | Confirmed | TA-01 (TA-6); TA-02 (TA-7) -> WI-01 (US-9) | Re-run 2026-07-20 after DevInt reseed (TA-8/TA-9/US-12 wiped; recreated TA-6/TA-7 under US-9). On TA-6 set To Do=3 and logged Actual=2h via Task Detail; Estimate stayed blank instead of deriving 5. US-9 Task Roll-up read Estimate 4 / To Do 3 / Actual 2, so Total Estimate 4 != To Do 3 + Actual 2 = 5. Estimate is still an independent editable field (Add Task modal too). Actual is captured as a Time Logs entry-sum, not a manual actual_hours field. Completing a Task also zeroes its To Do. DEV-012 (badge shows 0) and DEV-014 (no inline edit) still reproduce. Positive: Task create and Task Detail routing now work. | DEV-013; DEV-015; DEV-016 | notes/E2E-08-10-TASK-PROPAGATION.md | 2026-07-20
E2E-09 | 9 | Phase 1 | Task Status | Complete all Tasks | Each Task becomes Completed and parent Story auto-changes to Completed | Latest BA Task propagation rule | Task Dashboard/Detail | Failed | Confirmed | TA-01 (TA-6); TA-02 (TA-7) -> WI-01 (US-9) | Partial. Completing only TA-6 (1 of 2) left US-9 at Defined (correct). Completing TA-7 as well auto-changed US-9 Schedule State to Completed - auto-complete works. But US-9 Flow State stayed Defined, so Schedule and Flow did not mirror and the parent is not fully Completed per BR-WI-01 / TASK-FR-016. Task Detail also exposes Schedule State + Flow State instead of a single Task State. | DEV-016; DEV-017 | notes/E2E-08-10-TASK-PROPAGATION.md | 2026-07-20
E2E-10 | 10 | Phase 1 | Task Reopen | Move one completed Task to In-Progress | Parent Story auto-moves to In-Progress; user still retains manual Work Item control | Latest BA Task propagation rule | Task Dashboard/Detail | Failed | Confirmed | TA-01 (TA-6) -> WI-01 (US-9) | Reopened TA-6 from Completed to In Progress; the Task change persisted after reload. US-9 stayed Completed and did NOT auto-roll-back to In-Progress. The reopen -> In-Progress rule (BR-TASK-02) is not implemented; the auto roll-up is one-way only. | DEV-016; DEV-018 | notes/E2E-08-10-TASK-PROPAGATION.md | 2026-07-20
E2E-11 | 11 | Phase 1 | Work Item Status | Walk Schedule/Flow through the six-state catalog | Both fields use Idea/Defined/In-Progress/Completed/Accepted/Release and mirror both ways | P1 Work Item Create/Detail confirmed catalog | Backlog; Work Item Detail; Iteration Status | Failed | Confirmed | US-7 / US-9 (probe) | Tested on US-7/US-9. Schedule State has 6 buttons (Idea..Release) but labels In Progress not In-Progress; Flow State dropdown has only 4 options (Defined/In Progress/Completed/Accepted), missing Idea and Release. Schedule<->Flow do NOT mirror either way: Schedule=In Progress left Flow Defined; Flow=Completed left Schedule In Progress. US-7 reverted to Defined/Defined. | DEV-020 | notes/E2E-11-13-STATUS-ITERATION.md | 2026-07-20
E2E-12 | 12 | Phase 2 | Iteration Acceptance | Set all scoped Story/Defect items to Accepted | Non-empty Iteration auto-changes to Accepted; user can still manually edit status | P2 Iterations lifecycle baseline | /iteration-status; /timeboxes | Failed | Confirmed | IT-01 (Sprint 26.2); US-7; US-9 | Set US-7 and US-9 (both Sprint 26.2 items) Schedule State = Accepted. Iteration Status ACCEPTED tile = 100% (13 of 13 pts) and iteration detail ACCEPTED 100% of committed, but Sprint 26.2 State stayed Planning in Timeboxes - did NOT auto-change to Accepted (BR-IT-02). Accepted metric correct; only the auto state transition is missing. | DEV-021 | notes/E2E-11-13-STATUS-ITERATION.md | 2026-07-20
E2E-13 | 13 | Phase 2 | No-lock / Manual Override | Manually change Iteration status and add/move scope | No status locks scope; authorized user retains manual status and assignment control | P2 Iterations lifecycle baseline | /timeboxes; /backlog | Passed | Confirmed | IT-2 (Sprint 26.1); DE-1 | Committed does NOT lock scope: added DE-1 to Committed Sprint 26.1 (scope 3->4, persisted) then removed it (4->3); both succeeded. Manual status: Commit/Accept Iteration buttons exist, but committing a 2nd iteration is blocked - Another iteration is already committed for this project (single Committed per project, not in business define; DEV-022). DE-1 restored to No iteration. | DEV-022 | notes/E2E-11-13-STATUS-ITERATION.md | 2026-07-20

## Business Baseline
Latest BA Business Baseline and SRS Reconciliation
Rule ID | Area | Latest BA Rule | Current SRS State | Conflict | E2E Expectation | Source / Note
BR-IT-01 | Iteration | Statuses are Planning, Committed and Accepted | Reconciliation confirms Committed; main P2 SRS is stale | Yes | New Iteration defaults Planning; assignment does not auto-commit; user may manually set Committed | Reconciliation 08 Confirmation Log C04
BR-IT-02 | Iteration | All non-empty scoped US/DE Accepted auto-accepts Iteration; manual override remains | P2 Iterations aligned | No | Verify automatic Accepted and continued manual edit | P2 Iterations 10.1
BR-IT-03 | Iteration | No status locks scope | P2 Iterations aligned | No | Add/move Work Item after status changes | P2 Iterations 10.1
BR-REL-01 | Release | Statuses Planning, Active, Accepted | P3 Release aligned | No | Only exact status values are available | P3 Release DC-004
BR-REL-02 | Work Item Release | One Work Item has at most one active Release | P3 Release and Milestone SRS aligned | No | Selecting a new Release replaces the prior Release and persists | Reconciliation 08 Confirmation Log C01
BR-MS-01 | Milestone | Release/Milestone are many-to-many and independent | P3 Milestone aligned at entity level | No | Create in either order; changing one relation preserves the other | P3 Milestones Data Source Rules
BR-MS-02 | Milestone Dates | Start = earliest linked Release start; End = latest linked Release end | P3 Milestone aligned | No | Link two Releases and verify derived read-only dates | P3-MS-FR-011..013
BR-WI-01 | Work Item State | Schedule and Flow share six values and mirror | P1 Work Item aligned | No | Verify defaults and both-way mirroring on same ID | WIC-FR-012..013; WID-FR-012
BR-TASK-01 | Task State | Defined, In-Progress, Completed | P1 Task aligned | No | Verify exact values and default Defined | TASK-FR / validation
BR-TASK-02 | Task Roll-up | All Tasks Completed -> parent Completed; reopen -> parent In-Progress | Not fully reflected in current Task SRS | Yes | Verify both automatic directions and manual parent override | Latest BA confirmation
BR-TIME-01 | Task Time | Estimate is read-only To Do + Actuals | P1 Task/Time SRS allows independent Estimate | Yes | Edit inputs and verify row/total formula | Latest BA confirmation
BR-ID-01 | Identity | Backlog, Detail and Iteration Status show one shared Work Item | P2 aligned | No | No clones; same key across screens | P2 Iteration Status business flow

## Test Data
Controlled DevInt Test Data
Data ID | Entity | Audit Name | DevInt Key/ID | Project | Team | Start Date | End Date | Initial Status | Current Status | Relations | Cleanup | Notes
CTX-01 | Context | BA-E2E-20260720 |  | NXP | Not Testable; No team used |  |  |  | Not Testable |  | Keep | BA directed continuation without Team because Team data is unavailable
IT-01 | Iteration | BA-E2E-20260720 Iteration | IT-5 | NXP | No team | 2026-07-21 | 2026-08-03 | Planning | Wiped (reseed) |  | Keep | Created once and persisted after reload ¦ Wiped on 2026-07-20 DevInt reseed (iterations now only Sprint 26.1/26.2)
REL-01 | Release | BA-E2E-20260720 Release A | Created; key not shown | NXP | Project-level | 2026-07-20 | 2026-08-15 | Planning | Wiped (reseed) | MS-01 | Keep | Created once and persisted; earlier start ¦ Wiped on 2026-07-20 DevInt reseed
REL-02 | Release | BA-E2E-20260720 Release B | Created; key not shown | NXP | Project-level | 2026-08-01 | 2026-08-31 | Planning | Wiped (reseed) | MS-01 | Keep | Created once and persisted; later end ¦ Wiped on 2026-07-20 DevInt reseed
MS-01 | Milestone | BA-E2E-20260720 Milestone | Created; key not shown | NXP | Project-level | 2026-07-20 | 2026-08-31 | Planned | Wiped (reseed) | REL-01; REL-02 not selectable | Keep | Standalone creation persisted ¦ Wiped on 2026-07-20 DevInt reseed
WI-01 | Story | BA-E2E-20260720 Story / existing surrogate | US-9 | NXP | Existing membership; Team behavior not testable |  |  | Defined (existing) | Completed (Schedule); Flow Defined; Sprint 26.2 | IT-01; REL-02; planned MS-01 | Keep | Reseed 2026-07-20: surrogate is now US-9 (was US-12). Assigned Sprint 26.2; Schedule Completed via Task roll-up, Flow stayed Defined; no Milestone field.
TA-01 | Task | BA-E2E-20260720 Task A | TA-6 | NXP inherited | No team inherited |  |  | Defined | In Progress | WI-01 / US-12 | Keep | Reseed 2026-07-20: now TA-6 under US-9. In Progress; To Do 0, Actual 2h (Time Logs). Estimate blank.
TA-02 | Task | BA-E2E-20260720 Task B | TA-7 | NXP inherited | No team inherited |  |  | Defined | Completed | WI-01 / US-12 | Keep | Reseed 2026-07-20: now TA-7 under US-9. Completed; Estimate 4, To Do 0, Actual 0.

## Execution Log
Business E2E Execution Log
Execution ID | Step ID | Timestamp | Surface | Action | Expected | Actual | Result | Evidence | Notes
EXEC-001 | E2E-00 | 2026-07-20 | App shell / Timeboxes | Verify signed-in context and available Team | A valid Project/Team context is available for controlled records | Hieu Vu Minh Bui; ACME Corp / NXP / All Teams. Team Alpha is selectable but is not linked to NXP. | Blocked | evidence/E2E-01/02-team-not-linked.png | Cannot establish valid Iteration Team context
EXEC-002 | E2E-01 | 2026-07-20 | Plan > Timeboxes > New Iteration | Create BA-E2E-20260720 Iteration for Team Alpha | Create once with default Planning and a Team compatible with the selected Project | The status catalog matches reconciliation, but submit is rejected with Team is not linked to this project; no record created in this attempt. | Blocked | evidence/E2E-01/01-create-form.png; evidence/E2E-01/02-team-not-linked.png | Dates were accepted; the first attempt was blocked only by unavailable Team test data
EXEC-003 | E2E-01 | 2026-07-20 | Plan > Timeboxes > New Iteration | Retry with No team per BA direction and reload list | Exactly one record persists with default Planning and the confirmed Planning/Committed/Accepted catalog | IT-5 created once and persisted after reload with Planning and 2026-07-21..2026-08-03; status catalog matches reconciliation. | Passed | evidence/E2E-01/03-create-no-team.png; evidence/E2E-01/04-created-persisted.png | Team scope remains Not Testable; Project and Type fields remain a confirmed UI enhancement
EXEC-004 | E2E-02 | 2026-07-20 | Top-level Releases > Create Release | Create Release A | Release A is created once with Planning and 2026-07-20..2026-08-15 | Release A created; total count changed from 2 to 3; row shows Planning and correct dates. | Passed | evidence/E2E-02/01-release-a-form.png | Current route is top-level /releases, not Timeboxes > Releases
EXEC-005 | E2E-02 | 2026-07-20 | Top-level Releases > Create Release | Create Release B | Release B is created once with Planning and 2026-08-01..2026-08-31 | Release B created; total count changed from 3 to 4; row shows Planning and correct dates. | Passed | evidence/E2E-02/02-release-b-form.png | Status options are exactly Planning, Active and Accepted
EXEC-006 | E2E-02 | 2026-07-20 | Releases list reload | Reload and count controlled releases | Each controlled Release appears exactly once and keeps values | Release A count = 1 and Release B count = 1 after reload; dates and Planning persisted. | Passed | evidence/E2E-02/03-releases-persisted.png | Creation and persistence pass
EXEC-007 | E2E-03 | 2026-07-20 | Plan > Milestones > New Milestone | Create standalone Milestone | Milestone may be created without Releases; default Planned; derived dates blank | Controlled Milestone created once with Planned; Target Start/End show blank because no Release was linked. | Passed | evidence/E2E-03/01-form-no-releases.png; evidence/E2E-03/02-milestone-persisted.png | Status catalog is Planned, At Risk, Met, Missed, Cancelled, Completed
EXEC-008 | E2E-03 | 2026-07-20 | New/Edit Milestone | Link Release A and B and verify derived dates | Both same-project controlled Releases are selectable; dates derive to 2026-07-20..2026-08-31 | Create and Edit both display No releases available despite both Releases existing and persisting in NXP. | Blocked | evidence/E2E-03/03-edit-no-releases.png | Cannot execute many-to-many linkage or date derivation
EXEC-009 | E2E-04 | 2026-07-20 | Backlog > Create Work Item | Inspect Story quick-create contract | Type, Title, Project, Team, Owner and Plan Estimate are available; Project defaults current and Team contains only valid linked options | Form shows Type, Title, Team, Owner and Plan Estimate but no Project. It offers No team and Team Alpha even though Team Alpha is not linked to NXP. | Failed | evidence/E2E-04/01-create-form.png | State defaults are server-side and cannot be accepted until a record is created
EXEC-010 | E2E-04 | 2026-07-20 | Backlog > Create Work Item | Create Story with No team per current BA test workaround | Exactly one Story is created in NXP | Submit returned An unexpected error occurred (ref: c13cf2d5-6ac5-4a87-aac2-5959c1a55fd2). | Blocked | evidence/E2E-04/02-no-team-unexpected-error.png | Generic error gives no actionable validation guidance
EXEC-011 | E2E-04 | 2026-07-20 | Backlog > Create Work Item | Retry controlled Story with Team Alpha | Only a Team linked to NXP is selectable and create succeeds | Submit returned Team is not linked to this project. | Blocked | evidence/E2E-04/03-team-not-linked.png | No valid Team is currently available for this Project
EXEC-012 | E2E-04 | 2026-07-20 | Backlog search | Search exact controlled title after both submits | One controlled Story exists only if a submit committed | No backlog items match your filters; no controlled Story was created. | Passed | evidence/E2E-04/04-no-record-after-attempts.png | Confirms there is no partial or ghost record
EXEC-013 | E2E-04 | 2026-07-20 | BA confirmation | Confirm Backlog findings and fallback | Dev gaps receive explicit disposition and testing may continue with an existing Work Item | BA directed DEV-007 and DEV-008 to Dev, reconfirmed DEV-009, and approved use of existing Work Items for later checkpoints. | Passed |  | E2E-04 remains functionally Blocked but its BA decision is closed
EXEC-014 | E2E-05 | 2026-07-20 | Backlog / US-12 | Assign existing US-12 to BA-E2E-20260720 Iteration inline | The selected Iteration is saved on the same Work Item | US-12 changed from Unscheduled to BA-E2E-20260720 Iteration in the Backlog row. | Passed | evidence/E2E-05/01-us12-before-assignment.png; evidence/E2E-05/02-us12-assigned-inline.png | Uses BA-approved existing-record fallback
EXEC-015 | E2E-05 | 2026-07-20 | Backlog reload / US-12 | Reload and search US-12 | The Iteration assignment persists and no clone is created | US-12 remained assigned to BA-E2E-20260720 Iteration after reload and exact-ID search returned one row. | Passed | evidence/E2E-05/03-us12-assignment-persisted.png | Backlog-side assignment and persistence pass
EXEC-016 | E2E-05 | 2026-07-20 | Iteration Status / All Teams | Open Iteration Status and select IT-5 | All Teams exposes current-project Iterations including IT-5 and its assigned Work Items | Screen says No iterations in this project/team yet even though Timeboxes lists IT-1 through IT-5. | Blocked | evidence/E2E-05/04-iteration-status-no-iterations.png | Cannot verify same-ID US-12 or Iteration totals
EXEC-017 | E2E-05 | 2026-07-20 | Iteration Status / Team Alpha | Check whether a Team context reveals Iteration Status | Diagnostic only because Team behavior is Not Testable | Team Alpha exposes Sprint 26.2 with US-1 and US-9, but not the No-team IT-5. | Partial | evidence/E2E-05/05-team-alpha-iteration-status.png | Confirms the screen is team-filtered; does not resolve the All Teams/no-team gap
EXEC-018 | E2E-05 | 2026-07-20 | BA confirmation | Decide All Teams scope | A clear scope decision closes the suspected All Teams gap | BA confirmed Iteration Status does not need All Teams support; valid Team context is the supported path. | Passed |  | DEV-010 accepted as-is; cross-screen retest waits for Team test data
EXEC-019 | E2E-06 | 2026-07-20 | Work Item Detail / US-12 | Assign Release A | One active Release can be selected and saved without changing Iteration | Release A saved on US-12; IT-5 remained selected. | Passed | evidence/E2E-06/02-us12-release-a.png | Matches the one-active-Release rule
EXEC-020 | E2E-06 | 2026-07-20 | Work Item Detail / US-12 | Change Release A to Release B and reload | Release B replaces A, persists, and leaves Iteration unchanged | Release B replaced A, remained selected after reload, and IT-5 remained selected. | Passed | evidence/E2E-06/03-us12-release-b-replaces-a.png; evidence/E2E-06/04-us12-release-b-persisted-no-milestone.png | Single-select Release behavior passes
EXEC-021 | E2E-06 | 2026-07-20 | Backlog / US-12 | Verify Release and Iteration mirror | Backlog shows the same Release B and IT-5 on the same US-12 | Exact-ID search showed one US-12 with Release B and BA-E2E-20260720 Iteration. | Passed | evidence/E2E-06/05-us12-release-b-backlog-mirror.png | Detail-to-Backlog identity and assignment mirror pass
EXEC-022 | E2E-06 | 2026-07-20 | Work Item Detail / US-12 | Assign eligible Milestone(s) | Milestone multi-select is present; with Release B, add-new options show only Milestones related to Release B | No Milestone field or control exists in Work Item Detail. | Blocked | evidence/E2E-06/04-us12-release-b-persisted-no-milestone.png | Cannot test multi-select, related filtering or preservation when Release changes
EXEC-023 | E2E-06 | 2026-07-20 | BA confirmation | Confirm DEV-011 | Missing Milestone control receives a clear Dev disposition | BA confirmed the proposed Work Item Milestone multi-select fix. | Passed |  | E2E-06 BA decision closed; functional result remains Blocked
EXEC-024 | E2E-07 | 2026-07-20 | Work Item Detail > Tasks | Open empty Task Dashboard | No child Tasks means count 0 and totals 0/0/0 | US-12 showed 0 Tasks, no rows and totals To Do 0h / Actuals 0h / Estimate 0h. | Passed | evidence/E2E-07/01-empty-task-dashboard.png | Clean starting state
EXEC-025 | E2E-07 | 2026-07-20 | Create Task modal | Inspect task-create fields | Create captures Name, Owner and initial To Do/Actuals inputs or derives read-only Estimate from them | Form contains Name, editable Estimate and Owner; it has no To Do or Actuals. | Failed | evidence/E2E-07/02-add-task-form.png | Conflicts with confirmed Estimate = To Do + Actuals rule
EXEC-026 | E2E-07 | 2026-07-20 | Work Item Detail > Tasks | Create controlled Task A | One child Task is created with default Defined and inherited context | TA-8 created once, defaulted Defined, showed NXP / no Team and Alice Developer. | Passed | evidence/E2E-07/03-task-a-created.png | Task row appeared under US-12
EXEC-027 | E2E-07 | 2026-07-20 | Work Item Detail > Tasks | Create controlled Task B | Second child Task is created once; tab count and totals update | TA-9 created once and defaulted Defined; two rows and 6h Estimate were visible, but the tab still showed 0 Tasks. | Failed | evidence/E2E-07/04-task-b-created-count-mismatch.png | Row data and count derive from different sources
EXEC-028 | E2E-07 | 2026-07-20 | Work Item Detail reload | Reload US-12 and reopen Tasks | Both Tasks persist; tab count equals 2; Task roll-up matches rows | TA-8 and TA-9 persisted and Detail roll-up showed Estimate 6 / To Do 0 / Actual 0, but the tab remained 0 Tasks. | Failed | evidence/E2E-07/05-tasks-persisted-after-reload.png | Persistence passes; count remains wrong
EXEC-029 | E2E-07 | 2026-07-20 | Backlog search | Search the controlled Task prefix | Child Tasks do not appear as Backlog rows | No backlog items matched BA-E2E-20260720 Task. | Passed | evidence/E2E-07/06-tasks-not-in-backlog.png | Backlog isolation passes
EXEC-030 | E2E-07 | 2026-07-20 | BA confirmation | Confirm DEV-012/013/014 | Task count, time contract and inline-edit dispositions are explicit | BA confirmed count must be correct, time must follow the defined business rule, and Task Dashboard must allow inline editing. | Passed |  | E2E-07 BA decision closed; functional result remains Failed
EXEC-031 | E2E-08 | 2026-07-20 | DevInt environment | Start Task time/status propagation test | DevInt is available and US-12 can be opened | DevInt was turned off; BA instructed testing to stop and resume later. | Blocked |  | Resume at E2E-08; do not recreate TA-8 or TA-9
EXEC-032 | E2E-08 | 2026-07-20 | Work Item Detail > Tasks / US-9 | Recreate controlled Tasks after reseed | Two child Tasks created once with default Defined and inherited context | TA-6 and TA-7 created once under US-9, default Defined, NXP / no team; TA-7 accepted an independent Estimate 4 with blank To Do/Actual | Passed | notes/E2E-08-10-TASK-PROPAGATION.md | Reseed wiped TA-8/TA-9; tab badge still shows 0 (DEV-012)
EXEC-033 | E2E-08 | 2026-07-20 | Task Detail / TA-6 | Set To Do=3 and log Actual=2h; observe Estimate | Estimate becomes read-only 5 (To Do + Actuals) | Estimate stayed blank; US-9 roll-up Estimate 4 != To Do 3 + Actual 2 = 5; Actual entered via Time Logs entry-sum | Failed | notes/E2E-08-10-TASK-PROPAGATION.md | DEV-013 / DEV-015 reconfirmed
EXEC-034 | E2E-09 | 2026-07-20 | Task Detail / TA-6 | Complete only TA-6 (1 of 2) | Parent stays not Completed | US-9 stayed Defined; completing TA-6 also zeroed its To Do | Passed | notes/E2E-08-10-TASK-PROPAGATION.md | Partial-completion guard correct
EXEC-035 | E2E-09 | 2026-07-20 | Task Detail / TA-7 | Complete TA-7 so all child Tasks are Completed | Parent Schedule and Flow both auto-change to Completed | US-9 Schedule State auto-Completed; Flow State stayed Defined (no mirror) | Failed | notes/E2E-08-10-TASK-PROPAGATION.md | DEV-017
EXEC-036 | E2E-10 | 2026-07-20 | Task Detail / TA-6 | Reopen TA-6 to In Progress | Parent auto-moves to In-Progress | TA-6 persisted In Progress after reload; US-9 stayed Completed, no roll-back | Failed | notes/E2E-08-10-TASK-PROPAGATION.md | DEV-018; auto roll-up one-way
EXEC-037 | E2E-05 | 2026-07-20 | Work Item Detail / US-9 | Assign US-9 to Sprint 26.2 (post-reseed retest) | Assignment persists and same ID appears in Iteration Status | US-9 assigned to Sprint 26.2; appears once in Iteration Status Sprint 26.2 with Schedule State C | Passed | notes/E2E-08-10-TASK-PROPAGATION.md | Cross-screen identity now testable after reseed
EXEC-038 | E2E-05 | 2026-07-20 | Track > Iteration Status / Sprint 26.2 | Verify US-9 roll-up metrics | Task Est/To Do totals roll up; active count reflects not-Completed tasks | Totals Task Est 4 / To Do 0 correct, but US-9 shows Tasks 100% and top tile 0 Active Tasks though TA-6 is In Progress | Failed | notes/E2E-08-10-TASK-PROPAGATION.md | DEV-019
EXEC-039 | E2E-05 | 2026-07-20 | Track > Team Status / Sprint 26.2 | Verify per-owner task roll-up | Same child Tasks roll to owner with correct counts | Alice Developer (2 Tasks) 50%, Estimate 4 / To Do 0 / Actuals 2 - state-based 50% disagrees with Iteration Status 100% | Partial | notes/E2E-08-10-TASK-PROPAGATION.md | Identity roll-up correct; metric inconsistent (DEV-019)

## Gap Log
Business E2E Gap Log
Gap ID | Step ID | Object/Screen | Expected Business | DevInt Actual | Gap Type | Severity | Recommendation | BA Decision | Owner | Retest | Evidence | Notes
DOC-001 | E2E-06 | Release/Milestone SRS | Work Item has at most one Release and may have multiple Milestones | Current Release and Milestone SRS already state this rule | Invalidated | - | No document change for Release cardinality; preserve the confirmed C01 rule | Invalidated | BA / Docs | Not Required |  | Tracker expectation was corrected against the final reconciliation log
DOC-002 | E2E-08 | Task/Time SRS | Estimate is read-only and equals To Do + Actuals | Current SRS allows Estimate as an independent input | Documentation | P0 | Reconcile Task Management and Time Tracking SRS plus mockup | Fix Direction Approved | BA / Docs | Not Run |  | Latest BA decision is authoritative
DEV-001 | E2E-01 | Timeboxes / New Iteration | Iteration states are Planning, Committed and Accepted | DevInt exposes the correct three states | Invalidated | - | No Dev change; reconcile the main Phase 2 SRS with the confirmed reconciliation record | Invalidated | BA / Docs | Not Required | evidence/E2E-01/01-create-form.png | BA reconfirmed on 2026-07-20 that Committed is valid
DEV-002 | E2E-01 | New Iteration quick create | Quick create includes and inherits active Project/Team context; selected Team must belong to Project | Form shows Team only, offers No team and Team Alpha, and does not show Project or Type | UI / Business | P1 | Add Type and Project; inherit Project from active context; keep Team behavior separately testable | Confirmed | Dev | Not Run | evidence/E2E-01/01-create-form.png | BA approved the proposed UI addition on 2026-07-20
DEV-003 | E2E-00; E2E-01 | Project/Team context | A valid linked Team can be selected when Team behavior is in test scope | Team Alpha is selectable but submit returns Team is not linked to this project | Test Data / Integration | P2 | Defer Team validation; provide linked Team data and rerun later | Confirmed | Dev / Test Data | Not Testable | evidence/E2E-01/02-team-not-linked.png | BA directed use of No team so the remaining business chain can continue
DEV-004 | E2E-02 | Release navigation | Phase 3 Release Management is accessed under Plan > Timeboxes; Portfolio > Release Planning is Future Phase 5 | DevInt exposes Releases as an active top-level navigation item at /releases | Navigation / Scope | P1 | Move current Release Management under Timeboxes and remove the top-level Releases entry | Confirmed | Dev | Not Run | evidence/E2E-02/03-releases-persisted.png | Matches the earlier DevInt-alignment decision
DEV-005 | E2E-02 | Releases list | Phase 3 shows Release assignment/readiness fields only; Release progress/tracking is Future Phase 5 | Current Phase 3-looking list exposes a Progress column | Scope Leakage | P1 | Remove/hide Progress from current Release Management; implement tracking later in Portfolio > Release Planning | Confirmed | Dev | Not Run | evidence/E2E-02/03-releases-persisted.png | Do not use the current dash/percentage as Phase 3 acceptance evidence
DEV-006 | E2E-03 | Milestone Associated Releases | Same-project Releases are selectable in Create/Edit; one Milestone may link multiple Releases and derive MIN start / MAX end | Create and Edit display No releases available although Release A and B exist in NXP | Business Integration | P0 | Load current-project Releases into the Milestone multi-select, persist many-to-many links, and recalculate derived dates on add/remove | Confirmed | Dev | Not Run | evidence/E2E-03/03-edit-no-releases.png | BA confirmed the gap and fix direction on 2026-07-20
DEV-007 | E2E-04 | Backlog Story creation | A valid create path produces exactly one Story in the active Project | No team returns a generic unexpected error; Team Alpha returns Team is not linked to this project; no record is created | Functional Blocker | P0 | Provide a valid current-Project Team path, prevent incompatible selections, return field-level validation, and ensure one successful create commit | Confirmed | Dev / Test Data | Not Run | evidence/E2E-04/02-no-team-unexpected-error.png; evidence/E2E-04/03-team-not-linked.png; evidence/E2E-04/04-no-record-after-attempts.png | BA directed this finding to Dev on 2026-07-20
DEV-008 | E2E-04 | New Work Item quick create | Quick create fields are Type, Title, Project, Team, Owner and Plan Estimate; Project defaults current and Team is filtered by Project | Project is absent; No team and an incompatible Team Alpha are both offered | UI / Business | P1 | Add required Project defaulted to current context; filter Team to active project membership; align requiredness/options with the confirmed mockup | Confirmed | Dev | Not Run | evidence/E2E-04/01-create-form.png | BA directed this finding to Dev on 2026-07-20; Iteration and Release stay out of quick create
DEV-009 | E2E-04; E2E-11 | Backlog state controls | Flow State is the six-button control; Schedule State is a dropdown; both use Idea/Defined/In-Progress/Completed/Accepted/Release and mirror | Only a Schedule State column is visible and it is rendered as the six-button control; Flow State is absent | UI / Business | P0 | Render the six-button control as Flow State, add Schedule State dropdown, use the exact catalog, and update both atomically in either direction | Confirmed | Dev | Not Run | evidence/E2E-04/04-no-record-after-attempts.png | BA already confirmed this presentation and mirror rule during DevInt alignment
DEV-010 | E2E-05 | Iteration Status / All Teams | Iteration Status is supported only under a valid selected Team; All Teams behavior is not required | All Teams shows no Iterations; Team Alpha exposes its linked Sprint 26.2 | Scope Decision | - | Do not implement All Teams for Iteration Status; retest same-ID and totals later with valid Team-linked data | Accepted As-Is | Dev / Test Data | Not Testable | evidence/E2E-05/04-iteration-status-no-iterations.png; evidence/E2E-05/05-team-alpha-iteration-status.png | BA explicitly confirmed no All Teams requirement on 2026-07-20
DEV-011 | E2E-06 | Work Item Detail Milestones | Work Item has a Milestone multi-select; without Release show valid current-project options, with Release show related add-new options while retaining selected Milestones | Work Item Detail has no Milestone field or control | Missing Function | P0 | Add Milestone multi-select, load valid scoped options, apply Release-related add-new filtering, preserve selected values across Release changes, and persist independently | Confirmed | Dev | Not Run | evidence/E2E-06/04-us12-release-b-persisted-no-milestone.png | BA confirmed the fix direction on 2026-07-20
DEV-012 | E2E-07 | Work Item Task tab count | Task tab count equals the total number of child Tasks created under the Work Item | TA-8 and TA-9 exist and persist, but the tab still displays 0 Tasks | Shared Data / Metric | P0 | Drive tab count from the same child Task collection used by the table and roll-up; refresh immediately after create/delete | Confirmed | Dev | Not Run | evidence/E2E-07/04-task-b-created-count-mismatch.png; evidence/E2E-07/05-tasks-persisted-after-reload.png | BA confirmed the count must be correct on 2026-07-20
DEV-013 | E2E-07; E2E-08 | Create Task time fields | Estimate is read-only and always equals To Do + Actuals | Create Task exposes editable Estimate and no To Do/Actuals fields | Business Contract | P0 | Replace editable Estimate with To Do and Actuals inputs or initialize both to zero; always calculate and display Estimate = To Do + Actuals | Confirmed | Dev | Not Run | evidence/E2E-07/02-add-task-form.png | BA confirmed the previously defined time business rule on 2026-07-20; also reconcile DOC-002
DEV-014 | E2E-07; E2E-08 | Task Dashboard inline editing | Task Dashboard supports inline Name, State, Owner, To Do and Actuals; Estimate is read-only derived | Rows render static text only; no inline inputs or selectors are exposed | Missing Function | P0 | Add inline controls for Name, State, Owner, To Do and Actuals; recalculate read-only Estimate and parent totals immediately | Confirmed | Dev | Not Run | evidence/E2E-07/04-task-b-created-count-mismatch.png | BA confirmed inline editing is required on 2026-07-20
DEV-015 | E2E-08 | Task time / Actual model | Estimate is read-only and equals To Do + Actuals; Actual is a manual value per confirmed Phase 1 | Estimate stays an independent editable field and does not derive (roll-up Estimate 4 != To Do 3 + Actual 2 = 5). Actual is captured as a Time Logs entry-sum, and completing a Task silently zeroes its To Do. | Business Contract | P1 | Make Estimate read-only and always derive To Do + Actuals at Task, roll-up and Add Task modal; capture Actual as a manual input as in the mockup (replace the Time Logs entry-sum); do not auto-zero To Do when a Task is completed. | Confirmed | Dev / BA / Docs | Not Run | notes/E2E-08-10-TASK-PROPAGATION.md | BA 2026-07-20: Estimate derived read-only; Actual is a MANUAL input as in the mockup (not the Time Logs entry-sum); completing a Task must not silently zero To Do. Reconfirms DEV-013 / DOC-002.
DEV-016 | E2E-08; E2E-09; E2E-10 | Task Detail state model | A Task has a single Task State (Defined, In-Progress, Completed) per BR-TASK-01 | Task Detail exposes Schedule State (six buttons) plus Flow State (four-option dropdown) - the Story/Defect model, not a single Task State. Label uses In Progress, not In-Progress. | UI / Business | P1 | Replace Schedule + Flow State on Task Detail/Dashboard with a single Task State control using the exact catalog Defined/In-Progress/Completed. | Confirmed | Dev | Not Run | notes/E2E-08-10-TASK-PROPAGATION.md | BA confirmed 2026-07-20: remove Schedule + Flow State on Task; Task Detail/Dashboard design must match the mockup single Task State (Defined/In-Progress/Completed).
DEV-017 | E2E-09 | Parent roll-up on all-Tasks-Completed | When all child Tasks are Completed the parent Schedule State AND Flow State both change to Completed and mirror (BR-WI-01; TASK-FR-016) | US-9 Schedule State auto-changed to Completed, but Flow State stayed Defined; the two fields did not mirror. | Business Contract | P0 | On auto roll-up set both Schedule and Flow State to Completed; enforce Schedule <-> Flow mirroring in both directions generally. | Confirmed | Dev | Not Run | notes/E2E-08-10-TASK-PROPAGATION.md | Auto-complete direction works; only the mirror is missing. BA confirmed 2026-07-20.
DEV-018 | E2E-10 | Parent roll-up on Task reopen | Reopening any child Task after all were Completed auto-moves the parent back to In-Progress (BR-TASK-02); manual control remains | Reopened TA-6 to In Progress and it persisted, but US-9 stayed Completed; the parent did not roll back. | Missing Function | P0 | Implement the reverse roll-up so reopening a child Task sets the parent to In-Progress; keep manual override. | Confirmed | Dev | Not Run | notes/E2E-08-10-TASK-PROPAGATION.md | Auto roll-up is currently one-way only. BA confirmed 2026-07-20.
DEV-019 | E2E-05 | Iteration Status vs Team Status task metric | Iteration Status header metrics per BA: Planned Velocity is deferred to Phase 5 (not defined yet); Iteration End counts days; Accepted is the percent of US/DE that are Accepted. Task active-count and Task percent use child Task State (not Completed) and agree with Team Status. | For US-9 (TA-6 In Progress, TA-7 Completed) Team Status shows Alice 2 Tasks 50% (state-based) but Iteration Status shows US-9 Tasks 100% and 0 Active Tasks (To-Do-based), so the two screens disagree. | Shared Data / Metric | P1 | Defer Planned Velocity to Phase 5; keep Iteration End as a day count; compute Accepted from US/DE in Accepted state; compute task active-count and Task percent from Task State consistently across Iteration Status and Team Status (not from To Do). | Confirmed | Dev | Not Run | notes/E2E-08-10-TASK-PROPAGATION.md | BA 2026-07-20: Planned Velocity to Phase 5; Iteration End day-count OK; Accepted counts US Accepted; task metric must be state-based and consistent with Team Status.
DEV-020 | E2E-11 | Work Item Schedule/Flow State | Schedule and Flow State both use all six values (Idea/Defined/In-Progress/Completed/Accepted/Release) and mirror bidirectionally | Flow State dropdown has only 4 options (missing Idea and Release); label In Progress not In-Progress; Schedule<->Flow do not mirror in either direction (verified on US-7). | Business Contract | P0 | Give Flow State the full six-value catalog with exact spelling In-Progress; mirror Schedule<->Flow bidirectionally on every manual and automatic change; match the mockup. | Confirmed | Dev | Not Run | notes/E2E-11-13-STATUS-ITERATION.md | BA confirmed 2026-07-20; design must match the mockup.
DEV-021 | E2E-12 | Iteration auto-Accept | A non-empty Iteration whose assigned US/DE are all Accepted auto-changes to Accepted (BR-IT-02); manual override remains; no auto-reverse | US-7 and US-9 set to Accepted; Iteration Status Accepted = 100% (13/13) and detail Accepted 100% of committed, but Sprint 26.2 stayed Planning - no auto-transition. | Missing Function | P1 | Auto-set the Iteration State to Accepted when all scoped US/DE are Accepted; keep manual override and do not auto-reverse. | Confirmed | Dev | Not Run | notes/E2E-11-13-STATUS-ITERATION.md | BA confirmed 2026-07-20: per SRS/mockup the Iteration must auto-change to Accepted when all US/DE are Accepted and must remain manually editable. Accepted metric is already correct; only the auto state transition is missing.
DEV-022 | E2E-13 | Iteration commit restriction | The business define does not limit the number of Committed iterations per project; the user retains manual status control | Committing a second iteration is blocked with Another iteration is already committed for this project. | Business / Validation | P1 | Allow multiple Committed iterations per project (remove the single-committed restriction). | Confirmed | Dev | Not Run | notes/E2E-11-13-STATUS-ITERATION.md | BA confirmed 2026-07-20 that multiple Committed iterations per project are allowed.