## Overview
MINI RALLY — PRODUCT EXECUTION PLAN
Single planning workbook ¦ Baseline: 2026-07-26 ¦ Scope: BA, FE DEV, DevInt and UAT through Phase 5
BA Tasks |  |  | DEV Tasks |  |  | Product Gate
Total | 30 |  | Total | 35 |  | BA baseline | Phase 0-5 governance aligned
Done | 22 |  | Done | 0 |  | DEV current | Phase 0-4 DevInt; Phase 5 production not started
Open | 8 |  | Open | 35 |  | Next gate | P5.2 Capacity Planning active; docs aligned and mockup implementation next
HOW TO USE THIS WORKBOOK
1. BA owns business rules, SRS/mockup alignment and acceptance. 2. Every Phase 5 feature follows: propose -> BA confirm -> docs align -> implement -> verify -> BA accept -> close. 3. BA/Mockup readiness and Production readiness are always separate. 4. Phase 5 closes only after P5.1-P5.3 close, tests/traceability pass and BA accepts; only then create the Phase 5 DEV handoff.
Phase 5 Order | 1 | P5.0 Rebaseline | 2 | P5.1 Closure | 3 | P5.2 Capacity -> P5.3 Tracking | 4 | P5.4 Closeout
Sources of truth: RECONCILED_SOURCE_OF_TRUTH.md, Phase 5/PHASE5_DEVELOPMENT_TRACKING.md, phase SRS/checklists, 06_Dev testing align and 07_Test Business/specs. The Phase 5 DEV handoff is created only after phase close.

## Phase Roadmap
MINI RALLY — PHASE ROADMAP
Product baseline 2026-07-26 ¦ P5-GOV v2 confirmed; DEV dates remain an editable proposal
Phase | Theme | Scope | BA Status | DEV Status | Current Gate | Target Start | Target End | Exit Criteria | Next Action
Phase 0 | Foundation | App shell, authentication, workspace and project context | Done | In Progress | DevInt | 2026-07-20 | 2026-07-24 | P0 documents and mockup reconciled; DevInt result recorded | Close confirmed DevInt gaps
Phase 1 | Core backlog | Projects, Teams/Users in Settings, backlog, work item and task management | Done | In Progress | DevInt | 2026-07-20 | 2026-07-31 | One consistent work-item flow and task roll-up behavior | Close task/status and navigation gaps
Phase 2 | Iteration planning | Iteration lifecycle, backlog assignment and iteration status metrics | Done | In Progress | DevInt | 2026-07-27 | 2026-08-07 | Planning/Committed/Accepted rules pass UAT | Close iteration and totals gaps
Phase 3 | Execution & quality | Team Status, Release/Milestone management and Defect flow | Done | In Progress | DevInt | 2026-08-03 | 2026-08-14 | Confirmed Phase 3 business rules pass DevInt | Close Release/Milestone and Quality gaps
Phase 4 | Governance | Notifications, roles/permissions, settings and audit | Done | Ready | UAT Prep | 2026-08-10 | 2026-08-28 | Phase 4 implementation matches SRS/mockup and permissions matrix | Start implementation and DevInt
Phase 5 | Portfolio | Portfolio Items, Capacity Planning and Release Tracking; Release Planning deferred | In Progress | Needs BA | P5.2 Capacity Planning | 2026-07-26 |  | P5.1-P5.3 BA accepted; Phase 5 tests and traceability complete; Phase 5 DEV handoff created | Implement P5.2 Capacity Planning after docs alignment
Future | Deferred scope | Team/Iteration boards, generic Reports, Theme/Initiative, Release Planning, burnup history and multi-Release scenarios | Future Backlog | Future Backlog | Backlog |  |  | Only promoted after BA/PO confirmation | Quarterly product review

## BA Tasks
MINI RALLY — BA EXECUTION PLAN
Business analysis, SRS, mockup, UAT and governance tasks
Task ID | Phase | Workstream | Task / Outcome | Deliverable / Source | Dependency | Priority | Status | Owner Role | Target Start | Target End | Acceptance / Definition of Done | Next Gate | Notes
BA-0001 | Phase 0 | Foundation | Confirm app shell, authentication, workspace and project-context behavior | Phase 0 SRS + mockup checklist | None | P0 | Done | BA | 2026-07-18 | 2026-07-20 | All Phase 0 screens use the same context and navigation model | DevInt verification | Reconciled baseline
BA-0002 | Phase 0 | Project | Confirm multi-project model and project-level context | Project SRS | BA-0001 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | User can manage multiple projects without cross-project data ambiguity | DevInt verification | Teams and users are managed under Settings
BA-0003 | Phase 0 | Testing | Maintain Phase 0 business scenarios and traceability | 07_Test Business/specs/PHASE0_TEST_SCENARIOS.md | BA-0001 | P1 | Done | BA/UAT | 2026-07-19 | 2026-07-20 | All Phase 0 requirements have positive and negative cases | Execute UAT
BA-0101 | Phase 1 | Backlog | Confirm shared work-item identity across Backlog and Iteration screens | Backlog and Work Item SRS | BA-0002 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Changing a work item in one screen is reflected everywhere | DevInt verification
BA-0102 | Phase 1 | Work Item State | Confirm Schedule State and Flow State use one mirrored lifecycle | RECONCILED_SOURCE_OF_TRUTH.md | BA-0101 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Idea, Defined, In-Progress, Completed, Accepted, Release; default Idea | DevInt verification | Defect State remains separate
BA-0103 | Phase 1 | Tasks | Confirm task lifecycle and parent roll-up/reopen rules | Task Management SRS | BA-0102 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | All tasks Completed -> parent Completed; reopening one -> parent In-Progress | DevInt verification | Manual parent status remains allowed
BA-0104 | Phase 1 | Settings | Move Teams and User Management under Settings gear | Manage Projects/Teams/Users SRS + mockup | BA-0002 | P1 | Done | BA | 2026-07-19 | 2026-07-20 | Manage Projects contains Projects only; admin entities are under Settings | DevInt verification
BA-0105 | Phase 1 | Testing | Maintain Phase 1 UAT and traceability pack | 07_Test Business/specs/PHASE1_TEST_SCENARIOS.md | BA-0101..0104 | P1 | Done | BA/UAT | 2026-07-19 | 2026-07-20 | Business scenarios cover create/edit/status/task roll-up | Execute UAT
BA-0201 | Phase 2 | Iteration Lifecycle | Confirm Planning -> Committed -> Accepted behavior | Iterations SRS | BA-0101 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Default Planning; user can manually change; auto-accept is convenience only | DevInt verification | No lock on committed sprint
BA-0202 | Phase 2 | Scope | Confirm backlog assignment does not auto-commit and scope can change during sprint | Iterations SRS | BA-0201 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | US/DE can be added while iteration runs; board does not auto-move cards | DevInt verification
BA-0203 | Phase 2 | Iteration Metrics | Confirm Task Active and Totals definitions | Iteration Status SRS + mockup | BA-0103 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Task Active counts all tasks under iteration US/DE; totals show Plan Estimate, Task Estimate, To Do | DevInt verification | List view only
BA-0204 | Phase 2 | Testing | Review Phase 2 DevInt results one screen at a time | 06_Dev testing align tracker | BA-0201..0203 | P0 | In Progress | BA/UAT | 2026-07-27 | 2026-08-07 | Each gap has Match/Gap, decision, owner and retest evidence | BA gap confirmation | Do not batch-confirm unknown gaps
BA-0301 | Phase 3 | Release/Milestone | Confirm Release and Milestone are independent M:N entities | Release and Milestone SRS | BA-0101 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Either entity can be created first; linkage is optional and non-hierarchical | DevInt verification
BA-0302 | Phase 3 | Work Item Links | Confirm work item supports zero/one Release and zero/many Milestones | RECONCILED_SOURCE_OF_TRUTH.md | BA-0301 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Release dropdown and related milestone dropdown follow confirmed cardinality | DevInt verification | Only related milestones are suggested
BA-0303 | Phase 3 | Milestone Dates | Confirm manual and release-derived milestone date modes | Milestone SRS | BA-0301 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | No releases: manual dates; linked releases: MIN start and MAX end, read-only | DevInt verification | Removing all release links restores manual editing
BA-0304 | Phase 3 | Team Status | Confirm inline task editing and totals | Team Status SRS + mockup | BA-0103 | P1 | Done | BA | 2026-07-19 | 2026-07-20 | Task Dashboard edits inline and reflects shared task data | DevInt verification | Team/Iteration Board deferred
BA-0305 | Phase 3 | Quality | Confirm Defect keeps Defect State plus mirrored work-item states | Quality/Defect SRS | BA-0102 | P1 | Done | BA | 2026-07-19 | 2026-07-20 | Defect State is distinct; Flow/Schedule lifecycle remains common | DevInt verification
BA-0306 | Phase 3 | Testing | Review Phase 3 DevInt gaps and accept fixes | 06_Dev testing align tracker | BA-0301..0305 | P0 | In Progress | BA/UAT | 2026-08-03 | 2026-08-14 | Release, Milestone, Team Status and Quality scenarios pass retest | BA gap confirmation
BA-0401 | Phase 4 | Notifications | Maintain confirmed notification SRS and mockup | Phase 4 Notification SRS/checklist | Phase 0-3 baseline | P1 | Done | BA | 2026-07-18 | 2026-07-20 | Notification triggers, read state and navigation targets are testable | DEV implementation
BA-0402 | Phase 4 | RBAC | Maintain roles/permissions matrix and UX rules | Roles & Permissions SRS | BA-0002 | P0 | Done | BA | 2026-07-18 | 2026-07-20 | Every action and screen has explicit permission behavior | DEV implementation
BA-0403 | Phase 4 | Settings/Audit | Maintain Settings and Audit scope | Settings & Audit SRS | BA-0402 | P1 | Done | BA | 2026-07-18 | 2026-07-20 | Configuration changes and auditable actions are defined | DEV implementation
BA-0404 | Phase 4 | Testing | Prepare Phase 4 UAT and traceability | 07_Test Business/specs/PHASE4_TEST_SCENARIOS.md | BA-0401..0403 | P1 | Ready | BA/UAT | 2026-08-10 | 2026-08-14 | Scenario pack is reviewed before DevInt begins | UAT readiness review
BA-0500 | Phase 5 | Governance | Rebaseline Phase 5 scope, order, readiness and confirmation gates | Product workbook + Phase 5 tracker + Source of Truth | P5-GOV v1 | P0 | Done | Lead BA | 2026-07-26 | 2026-07-26 | Workbook, tracker, SRS, source of truth and handoff boundary agree | P5.1 proposal | No mockup behavior changed in P5.0
BA-0501 | Phase 5 | Portfolio Items | Close project/RBAC, field-data, Archive and test gaps | Phase 5/01_Portfolio_Items/SRS.md | BA-0500 | P0 | Done | BA/UX | 2026-07-26 |  | P5.1 Amendment v3 implementation verified and BA accepted; continue Phase 5 | BA accepted 2026-07-26 | P5.1 plus BA-confirmed Amendment v3 accepted 2026-07-26: shared Feature-linked Work Item flow, Backlog shows Unscheduled only, Task Estimate/To Do/Actual independent with complete setting To Do to 0. Build and runtime smoke completed; close P5.1 and continue Phase 5. Production API/persistence remains dev scope.
BA-0502 | Phase 5 | Release Planning | Define and accept Feature-to-Release planning board | Phase 5/02_Release_Planning/SRS.md | BA-0501 | P0 | Planned | BA/PO |  |  | Assign, move and unassign Features without duplicating Release management | Feature proposal | Starts only after P5.1 closes
BA-0503 | Phase 5 | Release Tracking | Define and accept Release KPI and Feature progress tracking | Phase 5/03_Release_Tracking/SRS.md | BA-0502 | P0 | Planned | BA/PO |  |  | Plan Estimate rollup, zero-estimate handling and no auto Release state pass UAT | Feature proposal | Burnup waits for trustworthy history
BA-0502 | Phase 5 | Capacity Planning | Define and accept single-Release Team capacity planning | Phase 5/02_Capacity_Planning/SRS.md | BA-0501 | P0 | In Progress | BA/PO | 2026-07-26 |  | Plan list, create modal, Teams by Total, allocations, publish and RBAC pass UAT | Docs alignment -> CAP-1 mockup | BA confirmed 2026-07-26: Rally child Projects map to Mini Rally Teams; one Draft/Published plan per Project+Release
BA-0503 | Phase 5 | Release Tracking | Define and accept Release KPI and Feature progress tracking | Phase 5/03_Release_Tracking/SRS.md | BA-0502 | P0 | Planned | BA/PO |  |  | Plan Estimate rollup, zero-estimate handling and no auto Release state pass UAT | Feature proposal | Starts after P5.2 Capacity Planning closes
BA-0504 | Phase 5 | Closeout | Close Phase 5 and publish the dedicated DEV handoff | Phase 5 test pack + traceability + Phase 5 DEV handoff | BA-0501..0503 | P0 | Planned | BA/UAT |  |  | P5.1-P5.3 closed; build/runtime/test evidence complete; BA accepts phase | DEV handoff | Handoff is created only after Phase 5 close
BA-0505 | Future | Release Planning | Keep Release Planning deferred until BA re-promotes it | Future_Backlog/02_Release_Planning.md | BA decision 2026-07-26 | P2 | Done | BA/PO | 2026-07-26 | 2026-07-26 | Active Phase 5 order no longer depends on Release Planning | Future backlog review | Capacity Planning publish is the active Phase 5 assignment mechanism

## DEV Tasks
MINI RALLY — DEV EXECUTION PLAN
Frontend/business implementation and DevInt tasks; schemas, DB and infrastructure are outside this plan
Task ID | Phase | Workstream | Task / Outcome | Deliverable / Source | Dependency | Priority | Status | Owner Role | Target Start | Target End | Acceptance / Definition of Done | Next Gate | Notes
DEV-0001 | Phase 0 | App Shell | Align navigation, project/workspace context and route guards with reconciled SRS | Phase 0 App Shell SRS | BA-0001 | P0 | In Progress | FE DEV | 2026-07-20 | 2026-07-24 | DevInt Phase 0 scenarios pass without context leakage | BA retest | No DB/infra change in this plan
DEV-0002 | Phase 0 | Project | Align multi-project selector and project-level page context | Phase 0 Project SRS | DEV-0001 | P0 | In Progress | FE DEV | 2026-07-20 | 2026-07-24 | Switching project refreshes all scoped screens consistently | BA retest
DEV-0003 | Phase 0 | Regression | Add/update FE tests for Phase 0 confirmed behavior | Phase 0 test scenarios | DEV-0001..0002 | P1 | Ready | DEV/QA | 2026-07-23 | 2026-07-24 | Automated checks cover critical routes and context | DevInt evidence
DEV-0101 | Phase 1 | Shared Work Item | Use one work-item model across Backlog, Iteration and detail views | Phase 1 Work Item SRS | DEV-0002 | P0 | In Progress | FE DEV | 2026-07-20 | 2026-07-29 | Edits are reflected across screens without duplicate state semantics | BA retest
DEV-0102 | Phase 1 | State Lifecycle | Implement mirrored Schedule State and Flow State options/default | BA-0102 | DEV-0101 | P0 | Ready | FE DEV | 2026-07-23 | 2026-07-29 | Both fields use Idea/Defined/In-Progress/Completed/Accepted/Release and default Idea | BA retest
DEV-0103 | Phase 1 | Tasks | Implement task status lifecycle, parent auto-complete and reopen roll-back | Task Management SRS | DEV-0101..0102 | P0 | Ready | FE DEV | 2026-07-27 | 2026-07-31 | All tasks Completed -> parent Completed; any reopened -> parent In-Progress | BA retest | Manual parent override remains possible
DEV-0104 | Phase 1 | Task Dashboard | Enable inline task editing with consistent values and validation | Task Management/Team Status SRS | DEV-0103 | P1 | Ready | FE DEV | 2026-07-29 | 2026-07-31 | Inline edit persists and all dependent totals refresh | BA retest
DEV-0105 | Phase 1 | Settings Navigation | Move Teams and User Management entry points under Settings gear | Manage Projects/Teams/Users SRS | DEV-0001 | P1 | Ready | FE DEV | 2026-07-27 | 2026-07-29 | Projects screen has no Teams tab; Settings contains Teams/Users | BA retest
DEV-0106 | Phase 1 | Regression | Add/update FE tests for work-item/task roll-up and Settings navigation | Phase 1 test scenarios | DEV-0101..0105 | P1 | Ready | DEV/QA | 2026-07-30 | 2026-07-31 | Critical Phase 1 cases pass in CI/DevInt | DevInt evidence
DEV-0201 | Phase 2 | Iterations | Implement Planning/Committed/Accepted with manual transitions | Iterations SRS | DEV-0101 | P0 | Ready | FE DEV | 2026-07-27 | 2026-08-03 | New iteration defaults Planning; all transitions remain user-editable | BA retest
DEV-0202 | Phase 2 | Auto Acceptance | Auto-set iteration Accepted when all assigned non-empty US/DE are Accepted | Iteration SRS | DEV-0201 | P0 | Ready | FE DEV | 2026-07-30 | 2026-08-04 | Automation is convenience only; no auto-reverse or status lock | BA retest
DEV-0203 | Phase 2 | Scope Changes | Allow adding/removing US/DE during Committed iteration without board auto-moves | Iteration SRS | DEV-0201 | P0 | Ready | FE DEV | 2026-07-30 | 2026-08-04 | Scope remains editable during sprint and assignment does not auto-commit | BA retest
DEV-0204 | Phase 2 | Iteration Status | Align list view columns, Task Active and Totals calculations | Iteration Status SRS | DEV-0103 | P0 | Ready | FE DEV | 2026-08-03 | 2026-08-06 | Totals show Plan Estimate, Task Estimate, To Do; Task Active uses all created tasks | BA retest | No active board view
DEV-0205 | Phase 2 | Regression | Add/update FE tests for iteration lifecycle, scope and metrics | Phase 2 test scenarios | DEV-0201..0204 | P1 | Ready | DEV/QA | 2026-08-06 | 2026-08-07 | Phase 2 critical cases pass and evidence is attached | DevInt sign-off
DEV-0301 | Phase 3 | Team Status | Use shared task data, inline edit and board-level totals | Team Status SRS | DEV-0103..0104 | P0 | Ready | FE DEV | 2026-08-03 | 2026-08-07 | Team Status changes immediately reflect in work item and iteration metrics | BA retest
DEV-0302 | Phase 3 | Release | Implement Release registry and zero/one Release selector on work items | Release Management SRS | DEV-0101 | P0 | Ready | FE DEV | 2026-08-03 | 2026-08-07 | Release can exist independently and work-item cardinality is enforced | BA retest
DEV-0303 | Phase 3 | Milestone | Implement zero/many Milestones per work item and M:N Release links | Milestone SRS | DEV-0302 | P0 | Ready | FE DEV | 2026-08-05 | 2026-08-11 | Milestones remain independent and can span multiple projects/teams | BA retest
DEV-0304 | Phase 3 | Milestone Dates | Implement manual dates and derived MIN/MAX mode when releases are linked | Milestone SRS | DEV-0303 | P0 | Ready | FE DEV | 2026-08-07 | 2026-08-12 | Linked releases make dates read-only; unlinking all restores manual editing | BA retest
DEV-0305 | Phase 3 | Related Milestones | Filter work-item Milestone dropdown using the selected Release relationship | Release/Milestone SRS | DEV-0302..0304 | P1 | Ready | FE DEV | 2026-08-10 | 2026-08-12 | Only related milestones are suggested while explicit existing links remain visible | BA retest
DEV-0306 | Phase 3 | Quality | Keep separate Defect State plus common mirrored Flow/Schedule lifecycle | Quality/Defect SRS | DEV-0102 | P1 | Ready | FE DEV | 2026-08-10 | 2026-08-13 | Defect-specific and common state fields do not overwrite each other | BA retest
DEV-0307 | Phase 3 | Navigation | Keep Release management under Plan > Timeboxes and Portfolio > Release Planning as Phase 5 placeholder | Navigation SRS/mockup | DEV-0001 | P1 | Ready | FE DEV | 2026-08-12 | 2026-08-13 | Navigation matches the confirmed phase boundary | BA retest
DEV-0308 | Phase 3 | Regression | Add/update FE tests for Team Status, Release/Milestone and Quality | Phase 3 test scenarios | DEV-0301..0307 | P1 | Ready | DEV/QA | 2026-08-13 | 2026-08-14 | Phase 3 scenarios pass with evidence | DevInt sign-off
DEV-0401 | Phase 4 | Notifications | Implement notification list, read/unread behavior and deep links | Notifications SRS/mockup | Phase 0-3 stable | P1 | Planned | FE DEV | 2026-08-10 | 2026-08-17 | All confirmed triggers and target routes pass UAT | DevInt
DEV-0402 | Phase 4 | RBAC | Implement role-aware visibility and action authorization feedback | Roles & Permissions SRS | DEV-0001 | P0 | Planned | FE DEV | 2026-08-10 | 2026-08-19 | Role matrix is enforced consistently on every relevant screen/action | Security/UAT review
DEV-0403 | Phase 4 | Settings | Implement confirmed settings screens and validation | Settings & Audit SRS | DEV-0402 | P1 | Planned | FE DEV | 2026-08-17 | 2026-08-21 | Settings behavior matches permissions and business validation | DevInt
DEV-0404 | Phase 4 | Audit | Implement audit list/filter/detail UX for confirmed events | Settings & Audit SRS | DEV-0402..0403 | P1 | Planned | FE DEV | 2026-08-19 | 2026-08-25 | Auditable actions are visible with actor, action, target and time | DevInt
DEV-0405 | Phase 4 | Regression | Add FE/component/E2E tests for Phase 4 governance | Phase 4 test scenarios | DEV-0401..0404 | P1 | Planned | DEV/QA | 2026-08-24 | 2026-08-28 | Phase 4 critical path passes before handoff | UAT sign-off
DEV-0501 | Phase 5 | Portfolio Items | Implement production Portfolio Items from the closed Phase 5 handoff | Future Phase 5 DEV handoff | BA-0501 + Phase 5 close | P0 | Needs BA | FE DEV |  |  | Project-scoped RBAC, Feature data, Archive and rollups pass DevInt | DevInt | Mockup implementation is not production authorization
DEV-0502 | Phase 5 | Release Planning | Implement Feature-to-Release planning | Future Phase 5 DEV handoff | DEV-0501 + BA-0502 | P0 | Needs BA | FE DEV |  |  | Assign/move/unassign is project-scoped and does not duplicate Release CRUD | DevInt
DEV-0503 | Phase 5 | Release Tracking | Implement Release KPI and Feature progress tracking | Future Phase 5 DEV handoff | DEV-0502 + BA-0503 | P0 | Needs BA | FE DEV |  |  | Confirmed rollup, zero-state and manual Release lifecycle pass DevInt | DevInt | No fabricated burnup history
DEV-0501 | Phase 5 | Portfolio Items | Implement production Portfolio Items from the closed Phase 5 handoff | Future Phase 5 DEV handoff | BA-0501 + Phase 5 close | P0 | Needs BA | FE DEV |  |  | Project-scoped RBAC, Feature data, Archive and rollups pass DevInt | DevInt | Mockup implementation is not production authorization
DEV-0502 | Phase 5 | Capacity Planning | Implement single-Release Team capacity planning | Future Phase 5 DEV handoff | DEV-0501 + BA-0502 | P0 | Needs BA | FE DEV |  |  | Plan list/detail, Team capacity, allocations, publish and RBAC pass DevInt | DevInt | Publish updates Feature Release/Team only; no child Story/Defect cascade
DEV-0503 | Phase 5 | Release Tracking | Implement Release KPI and Feature progress tracking | Future Phase 5 DEV handoff | DEV-0502 + BA-0503 | P0 | Needs BA | FE DEV |  |  | Confirmed rollup, zero-state and manual Release lifecycle pass DevInt | DevInt | No fabricated burnup history
DEV-0504 | Phase 5 | Regression | Add Phase 5 FE/component/E2E and authorization coverage | Phase 5 test scenarios + future DEV handoff | DEV-0501..0503 | P0 | Needs BA | DEV/QA |  |  | Portfolio critical path and role/project negative cases pass | UAT sign-off
DEV-G003 | Future | Deferred UI | Do not build Team/Iteration boards, generic Reports, Theme/Initiative, Release Planning, burnup history or multi-Release scenarios until prioritized | Future_Backlog | PO approval | P3 | Future Backlog | DEV |  |  | No hidden or partial implementation enters active navigation | Quarterly review

## Decision Log
MINI RALLY — DECISION & DEPENDENCY LOG
Confirmed cross-phase rules and Phase 5 governance decisions that BA, DEV and QA must follow
Decision ID | Area | Confirmed Decision | Status | Impact | Owner | Primary Source
D-001 | Project | Product supports multiple projects; context must stay project-scoped | Confirmed | Phase 0-5 | BA/DEV | Project SRS
D-002 | Teams/Users | Teams and User Management live under Settings gear; Manage Projects shows projects only | Confirmed | Phase 0-4 | FE DEV | Phase 1 SRS/mockup
D-003 | Work Item State | Schedule State and Flow State share Idea, Defined, In-Progress, Completed, Accepted, Release and mirror both ways; default Idea | Confirmed | Phase 1-5 | FE DEV | Source of truth
D-004 | Defect | Defect keeps a separate Defect State in addition to common Flow/Schedule states | Confirmed | Phase 3 | FE DEV | Quality SRS
D-005 | Task Roll-up | Task uses Defined, In-Progress, Completed; all completed auto-completes parent; reopen auto-returns parent to In-Progress; manual parent status remains available | Confirmed | Phase 1-3 | FE DEV | Task SRS
D-006 | Iteration | Planning -> Committed -> Accepted; user can always change manually; no status lock and no auto-reverse | Confirmed | Phase 2-3 | FE DEV | Iteration SRS
D-007 | Iteration Scope | US/DE can be added or removed while sprint is running; assignment does not auto-commit and board cards do not auto-move | Confirmed | Phase 2-3 | FE DEV | Iteration SRS
D-008 | Iteration Auto Accept | All assigned non-empty US/DE Accepted may auto-set iteration Accepted as convenience | Confirmed | Phase 2 | FE DEV | Iteration SRS
D-009 | Iteration Metrics | Task Active counts all created tasks under iteration US/DE; Totals show Plan Estimate, Task Estimate and To Do | Confirmed | Phase 2-3 | FE DEV | Iteration Status SRS
D-010 | Release/Milestone | Release and Milestone are independent; either can be created first; relationship is M:N | Confirmed | Phase 3-5 | FE DEV | Release/Milestone SRS
D-011 | Work Item Links | A work item supports zero/one Release and zero/many Milestones | Confirmed | Phase 1-5 | FE DEV | Source of truth
D-012 | Milestone Dates | Milestone without releases uses manual dates; with releases uses MIN linked start and MAX linked end and dates become read-only | Confirmed | Phase 3-5 | FE DEV | Milestone SRS
D-013 | Milestone Scope | Milestone can span multiple projects and teams | Confirmed | Phase 3-5 | BA/DEV | Source of truth
D-014 | Navigation | Phase 3 Release management stays under Plan > Timeboxes; active Portfolio dropdown uses Capacity Planning for P5.2 | Confirmed | Phase 3-5 | FE DEV | P5-GOV v2
D-015 | Release Navigation | Promoted to Phase 5 P5.3 after Capacity Planning; use Plan Estimate progress, separate zero-estimate items, no automatic Release state and no burnup until trustworthy history exists | Confirmed | Phase 5 | BA/PO | P5-GOV v2
D-016 | Release Tracking | Dates after 2026-07-26 in this workbook are proposed execution dates and may be re-baselined by BA/DEV leads | Confirmed | Cross-phase | BA/DEV Lead | This workbook
D-017 | Plan Dates | Phase 5 active MVP is Portfolio Items, Capacity Planning and Release Tracking; Release Planning is Future Backlog | Confirmed | Phase 5 | BA/PO | P5-GOV v2
D-018 | Phase 5 Scope | Execute P5.1 Portfolio Items -> P5.2 Capacity Planning -> P5.3 Release Tracking -> P5.4 Phase closeout and DEV handoff | Confirmed | Phase 5 | BA/DEV | P5-GOV v2
D-019 | Phase 5 Order | P5.1 is BA accepted and closed for BA/mockup scope; production implementation waits for Phase 5 DEV handoff | Confirmed | P5.1 | BA | P5.1 closure 2026-07-26
D-020 | Portfolio Readiness | Workspace Admin edits all Projects; Project Admin edits managed Projects; Project Member assigned context is read-only | Confirmed | P5.1-P5.3 | BA/DEV | P5-GOV v2
D-021 | Portfolio Access | Archive replaces hard delete; archived Features retain history and cannot receive new children | Confirmed | P5.1 | BA/DEV | P5-GOV v1
D-022 | Feature Archive | Release Planning is deferred; Capacity Planning publish is the active Feature Release/Team assignment mechanism for Phase 5 | Confirmed | Future/P5.2 | BA/DEV | BA decision 2026-07-26
D-023 | Release Planning | Use KPI + Feature list, Plan Estimate progress, separate zero-estimate items and no automatic Release transition | Confirmed | P5.3 | BA/DEV | P5-GOV v2
D-024 | Release Tracking | Capacity Planning uses Team rows, manual capacity, Draft/Published lifecycle, Project+Release uniqueness, single-Team Feature allocation and Publish to master Feature | Confirmed | P5.2 | BA/DEV | P5.2 Capacity SRS
D-025 | Capacity Planning | Each feature requires proposal, BA confirmation, docs, implementation, verification and BA acceptance; create DEV handoff only after Phase 5 closes | Confirmed | Phase 5 | BA/DEV/QA | P5-GOV v2
D-026 | Phase Gate | Each feature requires proposal, BA confirmation, docs, implementation, verification and BA acceptance; create DEV handoff only after Phase 5 closes | Confirmed | Phase 5 | BA/DEV/QA | P5-GOV v1
D-027 | Feature Work Items | Children of a Feature are Story/Defect Work Items; creation from Feature reuses the shared Work Item template and pre-fills Feature | Confirmed | P5.1 | BA/DEV | P5.1 Amendment v3
D-028 | Backlog Visibility | Plan > Backlog shows only Unscheduled Story/Defect; assigning Iteration removes it from Backlog and returning to Unscheduled brings it back | Confirmed | Phase 1-2/P5.1 | BA/DEV | P5.1 Amendment v3
D-029 | Task Hours | Task Estimate, To Do and Actual are independent; Estimate-first copies to To Do once; Completed sets To Do to 0; reopen does not restore To Do | Confirmed | Phase 1-2/P5.1 | BA/DEV | P5.1 Amendment v3