## Dashboard
Mini Rally Project Completion Dashboard
BA/Dev progress tracker for MVP through Phase 5. Current mandatory checkpoint: 2026-07-10.
Executive Summary
BA scope ready Phase docs/mockup readiness |  |  | Dev completion Production task completion |  |  | Jul 10 ready Hard milestone progress | Open risks Risks needing attention
66.67% |  |  | 50.34% |  |  | 57.14% | 5
Release Forecast
Scenario | Dev h/day | Buffered Dev h | Working days | Forecast End | Interpretation
Conservative | 8 | 160.44 | 21 | 2026-08-05 | Use this when evening workload is heavy.
Base | 10 | 160.44 | 17 | 2026-07-30 | Default plan for tracking.
Optimistic | 12 | 153.755 | 13 | 2026-07-24 | Use only if both devs can sustain 6h/night.
Jul 10 Required Scope |  | 50 | 5 | 2026-07-10 | Project, Team, Backlog, Timebox, Iteration Status, Milestone, Release.
Immediate next action |  |  |  |  | Start Phase 3 dev with Team Status, Release Management, Milestone core, then Quality > Defect dashboard.
Current Phase Status
Phase | BA Status | Dev Status | Estimate h | Tracker Status | Next Action
Phase 0 | BA Accepted | Done | 12 | Prod Gap Fixed | Verify architecture baseline.
Phase 1 | Ready for Dev | In Review | 16 | Prod Gap Fixed | Build Manage + Backlog foundations.
Phase 2.1 | Done | Done | 9 | Prod Gap Fixed | Build enhanced Backlog.
Phase 2.2 | Done | Done | 14 | Prod Gap Fixed | Build Iterations/Timeboxes.
Phase 2.3 | Done | In Review | 14 | Prod Gap Fixed | Build Iteration Status.
Phase 3 | Ready for Dev | Not Started | 44 | Ready | Develop Team Status, Release Management, Milestone core and Quality > Defect; confirm Milestone artifacts later.
Phase 4 | Future | Not Started | 52 | Future | Define governance after execution flows.
Phase 5 | Future | Not Started | 24 | Future | Define reporting after data stabilizes.
Post-MVP | Future | Not Started | 32 | Post-MVP | Portfolio optional after MVP.

## Assumptions
Assumptions
Editable planning inputs for the Mini Rally completion workbook.
Input | Value | Notes
Start Date | 2026-07-07 | Default start date for planning.
Target Jul 10 | 2026-07-10 | Hard milestone from BA.
Dev Count | 2 | Current project has 2 developers.
BA Count | 1 | Current project has 1 BA.
Conservative Dev Hours / Dev / Day | 4 | Evening work lower bound.
Base Dev Hours / Dev / Day | 5 | Default forecast basis.
Optimistic Dev Hours / Dev / Day | 6 | Evening work upper bound.
Base BA Hours / Day | 300% | Editable default for BA follow-up/spec review.
Buffer % | 0.2 | Applied to forecast estimates.
Working Days / Week | 5 | Weekend excluded by default.
Forecast Scenario | Base | Valid values: Conservative, Base, Optimistic.

## Phase Roadmap
Phase Roadmap
Phase-level plan from Foundation to MVP reporting. Portfolio remains Post-MVP.
Phase | Theme | BA Status | Dev Status | Primary Owner | Dev Estimate h | BA Estimate h | Priority | Confidence | Build Scope | Dependency | Notes | Tracker Status | Dev Days Base | Forecast End
Phase 0 | Foundation | BA Accepted | Done | Dev | 12 | 4 | High | Medium | Rally prod FE/app shell/auth/project-team context gap fixes are applied in commit 74b1ab8. | None | Runtime BA smoke passed; keep permission/error-state follow-ups visible. | Prod Gap Fixed | 0 | 2026-07-07
Phase 1 | Core Work Management | Ready for Dev | In Review | Dev + BA | 16 | 8 | High | High | Manage Projects/Teams/Users, Backlog, Work Item Create/Detail, Task, Time, Content, Activity are covered in Rally prod FE. | Phase 0 | Most flows pass; Task owner/history and attachment tooling remain follow-up. | Prod Gap Fixed | 0.28 | 2026-07-08
Phase 2.1 | Backlog Enhancement | Done | Done | Dev | 9 | 2 | High | High | Backlog Manage Filters, sort, rank, bulk controls and Iteration/Release assignment are applied in Rally prod FE. | Phase 1 Backlog | Browser BA flow passed. | Prod Gap Fixed | 0 | 2026-07-08
Phase 2.2 | Timeboxes / Iterations | Done | Done | Dev | 14 | 2 | High | High | Timeboxes/Iterations list, create and detail are applied in Rally prod FE. | Phase 1 + P2.1 | Browser BA flow passed; Releases/Milestones remain Phase 3. | Prod Gap Fixed | 0 | 2026-07-08
Phase 2.3 | Iteration Status | Done | In Review | Dev | 14 | 2 | High | High | Iteration Status selector, metrics, Add Item, filters and detail integration are applied in Rally prod FE. | P2.1 + P2.2 | Flow passed on mockup iteration; column-shape and seed linkage cleanup remain. | Prod Gap Fixed | 0.49 | 2026-07-08
Phase 3 | Quality & Delivery | Ready for Dev | Not Started | BA + Dev | 44 | 10 | High | Medium | Team Status, Release Management, Milestone core and Quality > Defect dashboard. Team Board is moved to Phase 4. | Phase 2 | Mockup and SRS are ready for P3.1/P3.2/P3.3 core/P3.4 dashboard; Milestone artifact behavior remains deferred. | Ready | 5 | 2026-07-16
Phase 4 | Team Board & Governance | Future | Not Started | BA + Dev | 52 | 12 | Medium | Low | Team Board plus notifications, RBAC, Settings, Audit and permission hardening. | Phase 1-3 | Team Board moved out of Phase 3 by BA decision; define after core delivery flows are stable. | Future | 5.2 | 2026-07-27
Phase 5 | Reporting | Future | Not Started | BA + Dev | 24 | 6 | Medium | Low | Dashboard, Burndown, Velocity, Workload, Release Progress, Exports. | Phase 1-4 data | MVP reporting pack after operational data is reliable. | Future | 2.4 | 2026-07-30
Post-MVP | Portfolio | Future | Not Started | BA + Dev | 32 | 8 | Low | Low | Initiative, roadmap, cross-project tracking. | MVP decision | Optional; not included in MVP release forecast. | Post-MVP | 0 | 2026-07-30
Formulas:
Forecast End = WORKDAY('Assumptions'!$B5,CEILING(SUM(N5:[Dev Days Base])*(1+'Assumptions'!$B13),1))

## Build Tasks
Build Tasks
Detailed build checklist: what each phase needs to build, who owns it, estimate and release target.
ID | Phase | Workstream | Capability | Build Detail | BA Status | Dev Status | Dev Owner | BA Owner | Priority | Estimate h | Confidence | Dependency | Release Target | Target Date | Remaining h | Progress
P0-01 | Phase 0 | Foundation | DB/Auth baseline | Verify migrations, fixed company, admin seed, auth/session and project/team context API are production-ready. | BA Accepted | Done | Dev 1 | BA | High | 5 | High | None | MVP | 2026-07-08 | 0 | 100%
P0-02 | Phase 0 | Foundation | App shell and context | Wire protected routes, navigation, breadcrumb, context selector and access/error states. | BA Accepted | Done | Dev 2 | BA | High | 4 | Medium | P0-01 | MVP | 2026-07-08 | 0 | 100%
P0-03 | Phase 0 | Foundation | Project CRUD verification | Verify create/edit/archive/restore project, fixed workspace, permission enforcement and smoke tests. | BA Accepted | Done | Dev 1 | BA | High | 3 | Medium | P0-01 | Jul 10 | 2026-07-10 | 0 | 100%
P1-01 | Phase 1 | Manage | Create Project | Build Manage > Projects create/edit/deactive flow and project selector compatibility. | Ready for Dev | Done | Dev 1 | BA | Critical | 3 | High | P0-01 | Jul 10 | 2026-07-10 | 0 | 100%
P1-02 | Phase 1 | Manage | Create Team | Build Teams list and Team Info/Members modal; status Active/Deactive; members selectable with search. | Ready for Dev | Done | Dev 1 | BA | Critical | 3 | High | P1-01 | Jul 10 | 2026-07-10 | 0 | 100%
P1-03 | Phase 1 | Manage | Invite/Edit User | Build Users list and Invite/Edit User modal; assign user to teams only; user project access derives from Team -> Project. | Ready for Dev | Done | Dev 2 | BA | High | 2.5 | High | P1-02 | MVP | 2026-07-12 | 0 | 100%
P1-04 | Phase 1 | Backlog | Backlog base list | Build Story/Defect backlog list with selected Project/Team context, server search/filter/sort/pagination. | Ready for Dev | Done | Dev 2 | BA | Critical | 3 | High | P1-01,P1-02 | Jul 10 | 2026-07-10 | 0 | 100%
P1-05 | Phase 1 | Work Item | Create Work Item | Build Story/Defect quick create and create-with-details; Project/Team required and validated. | Ready for Dev | Done | Dev 2 | BA | Critical | 3 | High | P1-04 | Jul 10 | 2026-07-10 | 0 | 100%
P1-06 | Phase 1 | Work Item | Work Item Detail | Build full detail page with Details, Tasks, Revision History and right-panel fields. | Ready for Dev | Done | Dev 1 | BA | High | 4 | Medium | P1-05 | MVP | 2026-07-15 | 0 | 100%
P1-07 | Phase 1 | Task | Child Task flow | Build task list, add task modal, task detail, task estimates and parent validation. | Ready for Dev | In Review | Dev 2 | BA | High | 4 | Medium | P1-06 | MVP | 2026-07-16 | 1.4 | 65%
P1-08 | Phase 1 | Content | Time/content/activity | Persist Plan Estimate, To Do, Actual, Description, Notes, Attachments and Revision History. | Ready for Dev | In Review | Dev 1 | BA | Medium | 4 | Medium | P1-06 | MVP | 2026-07-17 | 1.4 | 65%
P2-01 | Phase 2.1 | Backlog Enhancement | Advanced list behavior | Add Manage Filters, column sorting, resizable columns, inline edit, rank reorder and bulk release/iteration assignment. | Done | Done | Dev 1 | BA | Critical | 9 | High | P1-04,P1-05 | MVP | 2026-07-18 | 0 | 100%
P2-02 | Phase 2.2 | Timeboxes | Create Timebox / Iteration | Build Plan > Timeboxes Iterations list, quick create, create-with-details and full Iteration detail. | Done | Done | Dev 2 | BA | Critical | 8 | High | P1-02,P2-01 | Jul 10 | 2026-07-10 | 0 | 100%
P2-03 | Phase 2.2 | Timeboxes | Assign backlog to Iteration | Expose Work Item Iteration field in Backlog list/detail and validate Project/Team match. | Done | Done | Dev 1 | BA | Critical | 6 | High | P2-02 | MVP | 2026-07-19 | 0 | 100%
P2-04 | Phase 2.3 | Iteration Status | Iteration Status page | Build Track > Iteration Status selector, metrics strip, list, filters, inline edit and detail integration. | Done | In Review | Dev 2 | BA | Critical | 10 | High | P2-02,P2-03 | Jul 10 | 2026-07-10 | 3.5 | 65%
P2-05 | Phase 2.3 | Iteration Status | Add item to Iteration | Create Story/Defect directly into selected Iteration and also show it in Backlog; reuse Backlog create-with-details flow. | Done | In Review | Dev 1 | BA | High | 4 | High | P2-04 | MVP | 2026-07-19 | 1.4 | 65%
P3-01 | Phase 3 | Team Status | Team Status | Build Team Status from Iteration Status template with iteration picker, owner grouping, inline capacity edit, task dropdown state and expandable columns. | Ready for Dev | Not Started | Dev 2 | BA | Critical | 10 | High | P2-04 | MVP | 2026-07-24 | 10 | 0%
P3-02 | Phase 3 | Release | Release Management | Build Release list/create/detail with Planning/Active/Accepted status, optional manual Version, inline editable dashboard columns and project-level detail. | Ready for Dev | Not Started | Dev 1 | BA | Critical | 10 | High | P1-05,P2-01 | MVP | 2026-07-25 | 10 | 0%
P3-03 | Phase 3 | Milestone | Milestone core | Build project-level Milestone list/create/detail similar to Release: multiple projects, teams and releases; target dates derived from linked releases; owner and status included. | Ready for Dev | Not Started | Dev 2 | BA | High | 10 | Medium | P3-02 | MVP | 2026-07-27 | 10 | 0%
P3-04 | Phase 3 | Quality | Quality > Defect dashboard | Build Quality > Defect dashboard using Backlog Defect data and columns: Rank, ID, Name, User Story, Severity, Priority, State, Flow State, Fixed In Build, Iteration, Submitted By, Owner. | Ready for Dev | Not Started | Dev 1 | BA | High | 14 | Medium | P1-06 | MVP | 2026-07-28 | 14 | 0%
P3-05 | Phase 3 | Milestone | Milestone artifacts | Confirm and implement Milestone artifact assignment behavior after BA review; placeholder tab exists but final flow is deferred. | Pending Confirm | Not Started | Dev 2 | BA | Medium | 4 | Low | P3-03 | MVP | 2026-07-29 | 4 | 0%
P3-06 | Phase 3 | Release | Release readiness note | No readiness checklist in app; users gather readiness from US/DE release notes. Keep release summary and notes editable. | Ready for Dev | Not Started | Dev 1 | BA | Medium | 2 | Medium | P3-02,P3-04 | MVP | 2026-07-29 | 2 | 0%
P4-01 | Phase 4 | Team Board | Team Board | Build board view from same work_items source, columns by schedule state, list/board toggle and card detail open. | Future | Not Started | Dev 1 | BA | High | 16 | Medium | P2-04,P3-04 | MVP | 2026-08-02 | 16 | 0%
P4-02 | Phase 4 | Governance | Notifications | Build in-app notifications for assigned, mentioned, comments, status, iteration/release dates and read/unread. | Future | Not Started | Dev 1 | BA | Medium | 10 | Low | Phase 1-3 | MVP | 2026-08-04 | 10 | 0%
P4-03 | Phase 4 | Governance | RBAC and permission hardening | Define and enforce workspace/project roles, action-level gating, backend permission codes and access denied states. | Future | Not Started | Dev 2 | BA | High | 12 | Medium | Phase 1-3 | MVP | 2026-08-06 | 12 | 0%
P4-04 | Phase 4 | Governance | Settings and audit | Project/workflow settings, labels, user admin rules, audit log and destructive confirmation patterns. | Future | Not Started | Dev 1 | BA | Medium | 14 | Low | P4-03 | MVP | 2026-08-07 | 14 | 0%
P5-01 | Phase 5 | Reporting | Dashboard and burndown | Build project/iteration dashboard, burndown, velocity, planned vs completed and blocked item rollups. | Future | Not Started | Dev 2 | BA | Medium | 10 | Low | Phase 1-4 data | MVP | 2026-08-09 | 10 | 0%
P5-02 | Phase 5 | Reporting | Operational reports | Build workload, defect summary, release progress, filters and export report capability. | Future | Not Started | Dev 1 | BA | Medium | 10 | Low | P5-01 | MVP | 2026-08-11 | 10 | 0%
P5-03 | Phase 5 | Reporting | Report QA and handoff | Verify report numbers against source records, permissions and export output. | Future | Not Started | Dev 2 | BA | Medium | 4 | Low | P5-02 | MVP | 2026-08-12 | 4 | 0%

## Jul 10 Milestone
Jul 10 Milestone
Hard checkpoint: by 2026-07-10, the MVP slice must cover Project, Team, Backlog, Iteration Status, Milestone and Release.
ID | Required Capability | Acceptance Meaning | Phase | Linked Task | Owner | Priority | Status | Estimate h | Confidence | Ready?
J10-01 | Create Project | Project can be created/edited from Manage and selected in context. | Phase 1 | P1-01 | Dev 1 | Critical | Done | 3 | High | Yes
J10-02 | Create Team | Team can be created under Project, edited, and used as context. | Phase 1 | P1-02 | Dev 1 | Critical | Done | 3 | High | Yes
J10-03 | Create Backlog | Story/Defect can be created in Backlog with Project/Team auto-fill. | Phase 1 | P1-04,P1-05 | Dev 2 | Critical | Done | 6 | High | Yes
J10-04 | Create Timebox | Iteration can be created from Timeboxes with dates/state/team. | Phase 2.2 | P2-02 | Dev 2 | Critical | Done | 8 | High | Yes
J10-05 | Iteration Status | Iteration Status reads selected Iteration and assigned backlog items. | Phase 2.3 | P2-04 | Dev 2 | Critical | In Review | 10 | High | No
J10-06 | Milestone | Milestone core mockup and SRS are ready; artifact behavior remains deferred for BA confirmation. | Phase 3 | P3-03 | Dev 2 | Critical | In Review | 10 | Medium | No
J10-07 | Release | Release Management mockup and SRS are ready for development. | Phase 3 | P3-02 | Dev 1 | Critical | In Review | 10 | High | No

## Capacity Plan
Capacity Plan
Scenario plan for evening delivery capacity. Change assumptions to refresh planning logic.
Scenario | Dev Count | Dev h / Day | Dev Capacity / Day | BA Count | BA h / Day | Buffer % | Notes | MVP Dev h | Buffered h | Working Days | Forecast End
Conservative | 2 | 4 | 8 | 1 | 2 | 20% | Lower evening capacity | 133.7 | 160.44 | 21 | 2026-08-05
Base | 2 | 5 | 10 | 1 | 3 | 20% | Default planning scenario | 133.7 | 160.44 | 17 | 2026-07-30
Optimistic | 2 | 6 | 12 | 1 | 3.5 | 15% | Upper evening capacity | 133.7 | 153.755 | 13 | 2026-07-24
Formulas:
Forecast End = WORKDAY('Assumptions'!$B5,[Working Days])

## Risks & Decisions
Risks & Decisions
Open risks and decisions that can change timeline, priority or scope.
ID | Risk / Decision | Phase | Impact | Mitigation / Decision | Owner | Status
R01 | Phase 0 tracking is superseded by newer architecture foundation. | Phase 0 | Medium | Keep Phase 0 old file as historical; verify architecture foundation before production. | BA/Tech | Open Risk
R02 | Production implementation is still not started in current tracking files. | All | High | Use this workbook as dev execution tracker and update daily. | BA/Dev | Open Risk
R03 | Phase 1 official timebox is 16h but detailed breakdown may exceed it. | Phase 1 | Medium | Keep cap and detailed estimates visible; report variance before scope expansion. | BA/Dev | Open Risk
R04 | Team Board must not be included in Phase 3. | Phase 3/4 | High | Workbook places Team Board in Phase 4 and keeps Team Status in Phase 3. | BA | Decided
R05 | Milestone artifact behavior is not fully confirmed. | Phase 3 | Medium | Core Milestone scope is ready; keep artifact tab/assignment behavior as deferred follow-up until BA confirms. | BA/Dev | Open Risk
R06 | Permissions matrix is not finalized. | Phase 2+ | Medium | Current mock assumes Workspace Admin; harden RBAC in Phase 4. | BA/Tech | Open Risk
R07 | Phase 0-2 prod gap fixes are applied, but several regression follow-ups remain. | Phase 0-2 | Medium | Track remaining Iteration Status columns, Task owner/history, seed linkage, attachments and FE automation as follow-up. | BA/Dev | In Review

## Source Notes
Source Notes
Auditable source files used to create this workbook. Paths are plain text so BA/dev can verify them.
Source | Used For | Path
Time line.md | Master timeline, Phase 2 closure, recommended build order and risks. | D:/Mini_Rally_pj/Time line.md
Project_developement_plan.md | Roadmap, phase scope and latest baseline decisions. | D:/Mini_Rally_pj/04_Developement_tracking/Project_developement_plan.md
PHASE0_DEVELOPMENT_TRACKING.md | Phase 0 historical 12h tracking and acceptance notes. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 0/PHASE0_DEVELOPMENT_TRACKING.md
PHASE1_DEVELOPMENT_TRACKING.md | Phase 1 official 16h cap and task plan. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 1/PHASE1_DEVELOPMENT_TRACKING.md
PHASE2_DEVELOPMENT_TRACKING.md | Phase 2 37h tracking, P2.1/P2.2/P2.3 tasks and context rules. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 2/PHASE2_DEVELOPMENT_TRACKING.md
Phase 3 Team Status SRS | Team Status scope and dashboard behavior ready for development. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/01_Team_Status/SRS.md
Phase 3 Release SRS | Release Management scope ready for development. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/02_Release_Management/SRS.md
Phase 3 Milestone SRS | Milestone core scope ready; artifact behavior deferred. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/03_Milestones/SRS.md
Phase 3 Quality Defect SRS | Quality > Defect dashboard scope ready. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/04_Quality_Defect/SRS.md
Rally prod commit | Current prod gap-fix baseline: feat(web): align BA mockups with Mini Rally Phase 0-2. | D:/QNSC/Workspace/rally @ 74b1ab8
RALLY_MINI_RALLY_ALIGNMENT_GAP.md | BA-facing alignment and remaining gap baseline. | D:/Mini_Rally_pj/output/RALLY_MINI_RALLY_ALIGNMENT_GAP.md
RALLY_TEST_EXECUTION_2026-07-07.md | Runtime BA/FE verification result for Rally Phase 0/1/2. | D:/Mini_Rally_pj/output/RALLY_TEST_EXECUTION_2026-07-07.md