## Dashboard
Mini Rally Project Completion Dashboard
Compressed BA/Dev time plan: finish execution through Phase 5 by 2026-07-20.
Executive Summary
Current BA scope ready Phase 0-3 docs/mockups |  |  | Dev completion Production task completion |  |  | P3 handoff ready Confirmed BA rules | Target finish Phase 5 complete by
100% |  |  | 52.07% |  |  | 100% | 2026-07-20
Compressed Target Forecast
Scenario | Dev h/day | Buffered Dev h | Calendar days | Forecast End | Interpretation
Target 20/07 | 13.4 | 106.7 | 8 | 2026-07-20 | Compressed plan required to finish Phase 5 on 2026-07-20.
Normal Base | 10 | 128.04 | 13 | 2026-07-25 | Misses target unless scope is reduced or capacity is increased.
Fallback | 8 | 128.04 | 17 | 2026-07-29 | High-risk path; move Phase 4/5 items back to backlog if capacity is unavailable.
Target Scope Through Phase 5 |  | 106.7 | 8 | 2026-07-20 | Target scope excludes Team Board; finish Phase 3 by 16/07, Phase 4 by 18/07, Phase 5 by 20/07.
Immediate next action |  |  |  |  | Run Phase 3 13-16/07, Phase 4 17-18/07, Phase 5 19-20/07. Keep scope frozen.
Current Phase Status
Phase | BA Status | Dev Status | Estimate h | Tracker Status | Next Action
Phase 0 | BA Accepted | Done | 12 | Completed | Verify architecture baseline.
Phase 1 | BA/SRS Ready | In Review | 16 | Dev In Review | Build Manage + Backlog foundations.
Phase 2.1 | BA/SRS Ready | In Review | 9 | Dev In Review | Build enhanced Backlog.
Phase 2.2 | BA/SRS Ready | In Review | 14 | Dev In Review | Build Iterations/Timeboxes.
Phase 2.3 | BA/SRS Ready | In Review | 14 | Dev In Review | Build Iteration Status.
Phase 3 | BA/SRS Ready | In Progress | 44 | Dev In Progress | Develop Team Status, Task Dashboard inline edit, Release, Milestone and Quality > Defect using confirmed BA rules.
Phase 4 | Planned | Not Started | 30 | Target 20/07 | Execute notifications, RBAC and settings/audit by 18/07; keep Team Board in Future Backlog.
Phase 5 | Planned | Not Started | 24 | Target 20/07 | Execute reporting dashboard, operational reports and QA handoff by 20/07.
Post-MVP | Future | Not Started | 32 | Post-MVP | Portfolio optional after MVP.

## Assumptions
Assumptions
Editable planning inputs for the Mini Rally completion workbook.
Input | Value | Notes
Workbook Updated | 2026-07-12 | Latest BA/doc status baseline after Part 1-5 confirmation and final audit.
Target Phase 5 Finish | 2026-07-20 | Compressed target: finish execution through Phase 5 by 2026-07-20.
Dev Count | 2 | Current project has 2 developers.
BA Count | 1 | Current project has 1 BA.
Conservative Dev Hours / Dev / Day | 4 | Evening work lower bound.
Target Dev Hours / Dev / Day | 6.7 | Required compressed target basis to finish Phase 5 by 2026-07-20.
Optimistic Dev Hours / Dev / Day | 9 | Upper compressed target; assumes parallel work and weekend support.
Base BA Hours / Day | 3 | Editable default for BA follow-up/spec review.
Buffer % | 20% | Applied to forecast estimates.
Calendar Days / Week | 7 | Compressed plan uses calendar days, including weekend support.
Forecast Scenario | Target 20/07 | Valid values: Target 20/07, Normal Base, Fallback.

## Phase Roadmap
Phase Roadmap
Compressed phase-level plan: finish execution through Phase 5 by 2026-07-20. Portfolio remains Post-MVP.
Phase | Theme | BA Status | Dev Status | Primary Owner | Dev Estimate h | BA Estimate h | Priority | Confidence | Build Scope | Dependency | Notes | Tracker Status | Dev Days Base | Target End
Phase 0 | Foundation | BA Accepted | Done | Dev | 12 | 4 | High | High | Foundation scope is accepted as baseline for the Mini Rally BA pack. | None | Testing document exists and Phase 0 is not in the current change scope. | Completed | 0 | 2026-07-12
Phase 1 | Core Work Management | BA/SRS Ready | In Review | Dev + BA | 16 | 8 | High | High | Projects, Teams, Users, Backlog, Work Item detail, Task, Time, Content and Activity are covered as the core work-management baseline. | Phase 0 | Testing document exists; keep remaining implementation defects as prod follow-up rather than BA scope change. | Dev In Review | 0.20896 | 2026-07-13
Phase 2.1 | Backlog Enhancement | BA/SRS Ready | In Review | Dev | 9 | 2 | High | High | Backlog filters, sorting, rank/order behavior, bulk assignment and Iteration/Release assignment are confirmed. | Phase 1 Backlog | No schema/infra changes in this BA pass. | Dev In Review | 0 | 2026-07-14
Phase 2.2 | Timeboxes / Iterations | BA/SRS Ready | In Review | Dev | 14 | 2 | High | High | Iterations default to Planning; assigning backlog into an Iteration means the team has committed scope. | Phase 1 + P2.1 | Status remains manual-first; system auto-status is convenience only. | Dev In Review | 0 | 2026-07-14
Phase 2.3 | Iteration Status | BA/SRS Ready | In Review | Dev | 14 | 2 | High | High | Iteration Status supports manual team execution; when all US/DE are Accepted the system may auto-mark Iteration Accepted, but user can override manually. | P2.1 + P2.2 | No lock: teams can still add US/DE while sprint is running. | Dev In Review | 0.36567 | 2026-07-15
Phase 3 | Agile Delivery Extensions | BA/SRS Ready | In Progress | BA + Dev | 44 | 10 | High | High | Team Status, Release Management, Milestones and Quality > Defect are confirmed for dev execution. Team Board is out of current Agile MVP. | Phase 2 | Task roll-up, manual status override, release/milestone assignment and quality dashboard rules are confirmed. | Dev In Progress | 3.3582 | 2026-07-16
Phase 4 | Collaboration & Governance | Planned | Not Started | BA + Dev | 30 | 8 | High | Medium | Notifications, RBAC/permissions, settings, audit and workflow governance. Team Board is excluded from this target and stays Future Backlog. | Phase 1-3 | Compressed execution window: finish Phase 4 by 2026-07-18. | Target 20/07 | 2.2388 | 2026-07-18
Phase 5 | Reporting | Planned | Not Started | BA + Dev | 24 | 6 | High | Medium | Dashboard, Burndown, Velocity, Workload, Release Progress and Exports. | Phase 1-4 data | Compressed execution window: finish Phase 5 by 2026-07-20. | Target 20/07 | 1.791 | 2026-07-20
Post-MVP | Portfolio | Future | Not Started | BA + Dev | 32 | 8 | Low | Low | Initiative, roadmap, cross-project tracking. | MVP decision | Optional; not included in MVP release forecast. | Post-MVP | 0 | Post-MVP

## Build Tasks
Build Tasks
Detailed build checklist: what each phase needs to build, who owns it, estimate and release target.
ID | Phase | Workstream | Capability | Build Detail | BA Status | Dev Status | Dev Owner | BA Owner | Priority | Estimate h | Confidence | Dependency | Release Target | Target Date | Remaining h | Progress
P0-01 | Phase 0 | Foundation | DB/Auth baseline | Verify migrations, fixed company, admin seed, auth/session and project/team context API are production-ready. | BA Accepted | Done | Dev 1 | BA | High | 5 | High | None | MVP | 2026-07-08 | 0 | 100%
P0-02 | Phase 0 | Foundation | App shell and context | Wire protected routes, navigation, breadcrumb, context selector and access/error states. | BA Accepted | Done | Dev 2 | BA | High | 4 | Medium | P0-01 | MVP | 2026-07-08 | 0 | 100%
P0-03 | Phase 0 | Foundation | Project CRUD verification | Verify create/edit/archive/restore project, fixed workspace, permission enforcement and smoke tests. | BA Accepted | Done | Dev 1 | BA | High | 3 | Medium | P0-01 | Jul 10 | 2026-07-10 | 0 | 100%
P1-01 | Phase 1 | Manage | Create Project | Build Manage > Projects create/edit/deactive flow and project selector compatibility. | Ready for Dev | Done | Dev 1 | BA | Critical | 3 | High | P0-01 | Jul 10 | 2026-07-10 | 0 | 100%
P1-02 | Phase 1 | Manage | Create Team | Build Teams list and Team Info/Members modal; status Active/Deactive; members selectable with search. | Ready for Dev | Done | Dev 1 | BA | Critical | 3 | High | P1-01 | Jul 10 | 2026-07-10 | 0 | 100%
P1-03 | Phase 1 | Manage | Invite/Edit User | Build Users list and Invite/Edit User modal; assign user to teams only; user project access derives from Team -> Project. | Ready for Dev | Done | Dev 2 | BA | High | 2.5 | High | P1-02 | MVP | 2026-07-12 | 0 | 100%
P1-04 | Phase 1 | Backlog | Backlog base list | Build Story/Defect backlog list with selected Project/Team context, server search/filter/sort/pagination. | Ready for Dev | Done | Dev 2 | BA | Critical | 3 | High | P1-01,P1-02 | Jul 10 | 2026-07-10 | 0 | 100%
P1-05 | Phase 1 | Work Item | Create Work Item | Build Story/Defect quick create and create-with-details; Project/Team required and validated. | Ready for Dev | Done | Dev 2 | BA | Critical | 3 | High | P1-04 | Jul 10 | 2026-07-10 | 0 | 100%
P1-06 | Phase 1 | Work Item | Work Item Detail | Build full detail page with Details, Tasks, Revision History and right-panel fields. | Ready for Dev | Done | Dev 1 | BA | High | 4 | Medium | P1-05 | MVP | 2026-07-15 | 0 | 100%
P1-07 | Phase 1 | Task | Child Task flow | Build task list, add task modal, task detail, task estimates and parent validation. | Ready for Dev | In Review | Dev 2 | BA | High | 4 | Medium | P1-06 | MVP | 2026-07-16 | 1.4 | 65%
P1-08 | Phase 1 | Content | Time/content/activity | Persist Plan Estimate, To Do, Actual, Description, Notes, Attachments and Revision History. | Ready for Dev | In Review | Dev 1 | BA | Medium | 4 | Medium | P1-06 | MVP | 2026-07-17 | 1.4 | 65%
P2-01 | Phase 2.1 | Backlog Enhancement | Advanced list behavior | Add Manage Filters, column sorting, resizable columns, inline edit, rank reorder and bulk release/iteration assignment. | Done | Done | Dev 1 | BA | Critical | 9 | High | P1-04,P1-05 | MVP | 2026-07-18 | 0 | 100%
P2-02 | Phase 2.2 | Timeboxes | Create Timebox / Iteration | Build Plan > Timeboxes Iterations list, quick create, create-with-details and full Iteration detail. | Done | Done | Dev 2 | BA | Critical | 8 | High | P1-02,P2-01 | Jul 10 | 2026-07-10 | 0 | 100%
P2-03 | Phase 2.2 | Timeboxes | Assign backlog to Iteration | Expose Work Item Iteration field in Backlog list/detail and validate Project/Team match. | Done | Done | Dev 1 | BA | Critical | 6 | High | P2-02 | MVP | 2026-07-19 | 0 | 100%
P2-04 | Phase 2.3 | Iteration Status | Iteration Status page | Build Track > Iteration Status selector, metrics strip, list, filters, inline edit and detail integration. | Done | In Review | Dev 2 | BA | Critical | 10 | High | P2-02,P2-03 | Jul 10 | 2026-07-10 | 3.5 | 65%
P2-05 | Phase 2.3 | Iteration Status | Add item to Iteration | Create Story/Defect directly into selected Iteration and also show it in Backlog; reuse Backlog create-with-details flow. | Done | In Review | Dev 1 | BA | High | 4 | High | P2-04 | MVP | 2026-07-19 | 1.4 | 65%
P3-01 | Phase 3 | Team Status | Team Status + Task roll-up | Build Team Status from Iteration Status template. Tasks are optional child records; when all child Tasks are Completed, parent US/DE can auto-complete, while user can still change status manually. | BA/SRS Ready | In Progress | Dev 2 | BA | Critical | 10 | High | P2-04 | 20/07 Target | 2026-07-13 | 5 | 50%
P3-02 | Phase 3 | Release | Release Management | Build Release list/create/detail with Planning/Active/Accepted status. A Story/Defect has one active Release assignment; readiness is interpreted by users from US/DE notes, not a locked checklist. | BA/SRS Ready | Not Started | Dev 1 | BA | Critical | 10 | High | P1-05,P2-01 | 20/07 Target | 2026-07-14 | 10 | 0%
P3-03 | Phase 3 | Milestone | Milestone core | Build project-level Milestone list/create/detail: multi project/team/release selection, target dates, owner/status and direct assignment of US/DE artifacts to the milestone. | BA/SRS Ready | Not Started | Dev 2 | BA | High | 10 | Medium | P3-02 | 20/07 Target | 2026-07-15 | 10 | 0%
P3-04 | Phase 3 | Quality | Quality > Defect dashboard | Build dedicated Quality > Defect dashboard using Backlog Defect data and columns: Rank, ID, Name, User Story, Severity, Priority, State, Flow State, Fixed In Build, Iteration, Submitted By, Owner. | BA/SRS Ready | Not Started | Dev 1 | BA | High | 14 | Medium | P1-06 | 20/07 Target | 2026-07-16 | 14 | 0%
P3-05 | Phase 3 | Task Dashboard | Inline edit in Task Dashboard | Task Dashboard supports inline edit for Task status and key fields. The auto-complete behavior is convenience only and does not lock manual US/DE status changes. | BA/SRS Ready | Not Started | Dev 2 | BA | Medium | 4 | Medium | P3-01 | 20/07 Target | 2026-07-16 | 4 | 0%
P3-06 | Phase 3 | Release | Release readiness note | No readiness checklist in app; users gather readiness from US/DE release notes. Keep release summary and notes editable. | BA/SRS Ready | Not Started | Dev 1 | BA | Medium | 2 | Medium | P3-02,P3-04 | 20/07 Target | 2026-07-16 | 2 | 0%
P4-01 | Phase 4 | Future Backlog | Team Board | Keep Team Board in Backlog for the future. Current Agile flow continues with Backlog, Iteration Status, Team Status, Release, Milestone and Quality views. | Future Backlog | Not Started | Dev 1 | BA | High | 0 | Medium | P2-04,P3-04 | Future | Future | 0 | 0%
P4-02 | Phase 4 | Governance | Notifications | Build in-app notifications for assigned, mentioned, comments, status, iteration/release dates and read/unread. | Planned | Not Started | Dev 1 | BA | Medium | 8 | Medium | Phase 1-3 | 20/07 Target | 2026-07-17 | 8 | 0%
P4-03 | Phase 4 | Governance | RBAC and permission hardening | Define and enforce workspace/project roles, action-level gating, backend permission codes and access denied states. | Planned | Not Started | Dev 2 | BA | High | 14 | Medium | Phase 1-3 | 20/07 Target | 2026-07-18 | 14 | 0%
P4-04 | Phase 4 | Governance | Settings and audit | Project/workflow settings, labels, user admin rules, audit log and destructive confirmation patterns. | Planned | Not Started | Dev 1 | BA | Medium | 8 | Medium | P4-03 | 20/07 Target | 2026-07-18 | 8 | 0%
P5-01 | Phase 5 | Reporting | Dashboard and burndown | Build project/iteration dashboard, burndown, velocity, planned vs completed and blocked item rollups. | Planned | Not Started | Dev 2 | BA | Medium | 10 | Medium | Phase 1-4 data | 20/07 Target | 2026-07-19 | 10 | 0%
P5-02 | Phase 5 | Reporting | Operational reports | Build workload, defect summary, release progress, filters and export report capability. | Planned | Not Started | Dev 1 | BA | Medium | 10 | Medium | P5-01 | 20/07 Target | 2026-07-20 | 10 | 0%
P5-03 | Phase 5 | Reporting | Report QA and handoff | Verify report numbers against source records, permissions and export output. | Planned | Not Started | Dev 2 | BA | Medium | 4 | Medium | P5-02 | 20/07 Target | 2026-07-20 | 4 | 0%

## Phase 3 Handoff
Phase 3 Handoff
Confirmed BA rules for Phase 3 development after Part 1-5 confirmation and final audit.
ID | Confirmed Point | Acceptance Meaning | Phase | Linked Task | Owner | Priority | Status | Estimate h | Confidence | Confirmed?
P3H-01 | Task roll-up | Child Tasks are optional. When all Tasks under a US/DE are Completed, that US/DE can auto-complete; user may still manually change status. | Phase 3 | P3-01,P3-05 | Dev 2 | Critical | Done | 10 | High | Yes
P3H-02 | Iteration lifecycle | Iteration starts Planning; assigning backlog commits sprint scope; all US/DE Accepted can auto-mark Iteration Accepted, but manual status override remains allowed. | Phase 2.3 | P2-04,P2-05 | Dev 2 | Critical | Done | 10 | High | Yes
P3H-03 | Team Status | Team Status remains a tracking view; no board lock and no restriction on adding US/DE while sprint is running. | Phase 3 | P3-01 | Dev 2 | Critical | Done | 10 | High | Yes
P3H-04 | Release Management | One active Release assignment per Story/Defect. Release status is user-managed; no readiness checklist lock. | Phase 3 | P3-02,P3-06 | Dev 1 | Critical | Done | 10 | High | Yes
P3H-05 | Milestones | Milestones can link multiple projects/teams/releases and assign US/DE artifacts directly. | Phase 3 | P3-03 | Dev 2 | High | Done | 10 | Medium | Yes
P3H-06 | Quality > Defect | Dedicated Quality > Defect dashboard uses Defect work items and keeps advanced actions such as delete/reopen/bulk for later. | Phase 3 | P3-04 | Dev 1 | High | Done | 14 | Medium | Yes
P3H-07 | Team Board | Team Board is not part of the current Agile MVP flow and is moved to Future Backlog. | Phase 4 | P4-01 | BA | Medium | Deferred | 0 | High | No

## Capacity Plan
Capacity Plan
Compressed delivery-capacity view for finishing through Phase 5 by 2026-07-20.
Scenario | Dev Count | Dev h / Day | Dev Capacity / Day | BA Count | BA h / Day | Buffer % | Notes | Target Remaining h | Buffered h | Calendar Days | Forecast End
Target 20/07 | 2 | 6.7 | 13.4 | 1 | 4 | 0% | Compressed target: calendar-day execution, parallel dev work, weekend support, no Team Board. | 106.7 | 106.7 | 8 | 2026-07-20
Normal Base | 2 | 5 | 10 | 1 | 3 | 20% | Normal evening capacity; likely misses 2026-07-20 unless scope is reduced. | 106.7 | 128.04 | 13 | 2026-07-25
Fallback | 2 | 4 | 8 | 1 | 2 | 20% | High-risk path; requires descoping or moving Phase 4/5 items back to backlog. | 106.7 | 128.04 | 17 | 2026-07-29
Formulas:
Forecast End = 'Assumptions'!$B5+[Calendar Days]

## Risks & Decisions
Risks & Decisions
Open risks and decisions that can change timeline, priority or scope.
ID | Risk / Decision | Phase | Impact | Mitigation / Decision | Owner | Status
R01 | Auto-status must not remove user control. | Phase 2/3 | High | Treat auto-complete as convenience only. Users can manually change Task, US/DE, Release, Milestone and Iteration status. | BA/Dev | Decided
R02 | Phase 3 development can drift if docs and mockups are not frozen. | Phase 3 | Medium | Use the confirmed Part 1-5 rules as the dev handoff baseline; schema/DB/infra remain out of scope for this BA pass. | BA/Dev | Open Risk
R03 | 20/07 finish target is compressed and capacity-sensitive. | Phase 3-5 | High | Keep scope frozen, exclude Team Board, run parallel dev tracks and include weekend/calendar-day support. | BA/Dev | Open Risk
R04 | Team Board must not be included in the current Agile MVP flow. | Phase 4/Future | High | Workbook places Team Board in Future Backlog and keeps Team Status as the Phase 3 tracking view. | BA | Decided
R05 | Milestone artifact behavior is confirmed at BA level. | Phase 3 | Low | Milestones may assign US/DE artifacts directly; no readiness checklist is required. | BA | Decided
R06 | Permissions matrix is not finalized. | Phase 4 | Medium | Define minimum RBAC/settings/audit scope needed for 20/07; move hardening extras to future backlog. | BA/Tech | Open Risk
R07 | Phase 0-3 testing and traceability need to stay synchronized as dev continues. | Phase 0-3 | Medium | Testing documents exist and should be updated when production behavior changes. | BA/QA | In Review

## Source Notes
Source Notes
Auditable source files used to create this workbook. Paths are plain text so BA/dev can verify them.
Source | Used For | Path
Time line.md | Master timeline, Phase 2 closure, recommended build order and risks. | D:/Mini_Rally_pj/Time line.md
Project_developement_plan.md | Roadmap, phase scope and latest baseline decisions. | D:/Mini_Rally_pj/04_Developement_tracking/Project_developement_plan.md
PHASE0_DEVELOPMENT_TRACKING.md | Phase 0 historical 12h tracking and acceptance notes. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 0/PHASE0_DEVELOPMENT_TRACKING.md
PHASE1_DEVELOPMENT_TRACKING.md | Phase 1 official 16h cap and task plan. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 1/PHASE1_DEVELOPMENT_TRACKING.md
PHASE2_DEVELOPMENT_TRACKING.md | Phase 2 37h tracking, P2.1/P2.2/P2.3 tasks and context rules. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 2/PHASE2_DEVELOPMENT_TRACKING.md
Phase 3 Team Status SRS | Team Status scope and dashboard behavior ready for development. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/01_Team_Status/SRS.md
Phase 3 Release SRS | Release Management scope ready for development. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/02_Release_Management/SRS.md
Phase 3 Milestone SRS | Milestone core scope ready; US/DE artifact assignment confirmed. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/03_Milestones/SRS.md
Phase 3 Quality Defect SRS | Quality > Defect dashboard scope ready. | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/04_Quality_Defect/SRS.md
Mini Rally doc commit | Latest committed BA/doc baseline after Phase 0-3 final audit. | D:/Mini_Rally_pj @ 7e68304a
Testing folder | Phase 0/1/2/3 testing documents, E2E flows and traceability matrix. | D:/Mini_Rally_pj/testing
RALLY_MINI_RALLY_ALIGNMENT_GAP.md | BA-facing alignment and remaining gap baseline. | D:/Mini_Rally_pj/output/RALLY_MINI_RALLY_ALIGNMENT_GAP.md
RALLY_TEST_EXECUTION_2026-07-07.md | Runtime BA/FE verification result for Rally Phase 0/1/2. | D:/Mini_Rally_pj/output/RALLY_TEST_EXECUTION_2026-07-07.md