## Dashboard
Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard | Mini Rally - Timeline Dashboard
BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started. | BA/Dev progress view generated from Time line.md. Green = done, blue = ready, amber = pending/next, gray = dev not started.
Phase 2 BA scope completed DONE | Phase 2 BA scope completed DONE |  | Phase 1 Ready for dev planning READY | Phase 1 Ready for dev planning READY |  | Phase 3 Next BA definition NEXT | Phase 3 Next BA definition NEXT |  | Production Implementation not started DEV | Production Implementation not started DEV
Phase 2 BA scope completed DONE | Phase 2 BA scope completed DONE |  | Phase 1 Ready for dev planning READY | Phase 1 Ready for dev planning READY |  | Phase 3 Next BA definition NEXT | Phase 3 Next BA definition NEXT |  | Production Implementation not started DEV | Production Implementation not started DEV
Phase 2 BA scope completed DONE | Phase 2 BA scope completed DONE |  | Phase 1 Ready for dev planning READY | Phase 1 Ready for dev planning READY |  | Phase 3 Next BA definition NEXT | Phase 3 Next BA definition NEXT |  | Production Implementation not started DEV | Production Implementation not started DEV
Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2.
Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2.
Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2.
Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2. | Current BA conclusion Phase 2 is complete for mockup/SRS handoff. Phase 3 is the next BA definition area. Production development is not started in the tracking files. Team Board, Team Status, Release Management and Milestones must stay out of Phase 2.
Metric | Value | Meaning |  | Owner | Doing now | Done | Next
BA completed / closed slices | 5 | Phase 0 accepted + Phase 2.1/2.2/2.3 closed + Phase 2 context rule |  | BA | Phase 3 scope definition | Phase 0/1/2 BA docs and mockups | Team Board/Team Status/Release/Milestone/Quality SRS
Ready for dev planning | 1 | Phase 1 baseline |  | Dev | No production work marked in tracker | None in tracking | Plan and implement Phase 1, then Phase 2
Next BA definition items | 5 | Team Board, Team Status, Release, Milestones, Quality/Defect
Production status | Not started | Development tasks still show 0% in tracking

## Master Timeline
Master Timeline | Master Timeline | Master Timeline | Master Timeline | Master Timeline | Master Timeline | Master Timeline | Master Timeline | Master Timeline | Master Timeline
End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio. | End-to-end phase view from foundation through future reporting/portfolio.
Order | Phase | Business Theme | Main Scope | BA Status | Docs Status | Dev Status | Est. Hours | Owner Track | Current Decision
1 | Phase 0 | Foundation | App Shell, Auth, fixed Company/Workspace, Project, Project/Team context | BA accepted | Existing docs; old tracking superseded | Done | 12 | BA | Keep as foundation baseline; align with architecture foundation before production.
2 | Phase 1 | Core Work Management | Backlog base, Story/Defect create, Work Item Detail, Tasks, Time Tracking, Content, Activity Log, Manage Projects/Teams/Users | Ready | SRS created and updated | Done | 16 | BA + Dev | Ready for development planning. Manage Teams/Users is part of Phase 1.
3 | Phase 2.1 | Backlog Enhancement | Search, Manage Filters, sort, inline edit, Release/Iteration assignment, rank reorder, Project/Team context | Done | SRS complete | In-progress | 9 | BA done / Dev next | Closed for BA handoff.
4 | Phase 2.2 | Timeboxes / Iterations | Iteration list, create, detail, Theme/Notes, Project/Team, assignment options for Backlog | Done | SRS complete | In-progress | 14 | BA done / Dev next | Closed for BA handoff. Releases/Milestones deferred to Phase 3.
5 | Phase 2.3 | Iteration Status | Iteration selector, metrics, list from Backlog assignment, Add Item, inline edit, Project/Team context | Done | SRS complete | In-progress | 14 | BA done / Dev next | Closed for BA handoff. Team Board/Team Status deferred.
6 | Phase 3.1 | Team Board / Team Status | Board view, Team Status rollup, drag/drop, WIP/transition rules | Pending | Pending BA confirmation | Not started |  | BA next | Define SRS and acceptance rules.
7 | Phase 3.2 | Release / Milestones | Release CRUD/readiness/detail, Milestones/delivery checkpoints | Pending | Pending | Not started |  | BA next | Define after Phase 3 priority is confirmed.
8 | Phase 3.3 | Quality / Defect | Defect lifecycle, severity/priority, environment, reproduce steps, verify/reopen | Pending | Pending | Not started |  | BA next | Define as its own Phase 3 slice.
9 | Phase 4 | Collaboration & Governance | Notifications, RBAC, Settings, Audit | Future | Pending | Not started |  | BA later | Later phase.
10 | Phase 5 | Reporting | Dashboard, burndown, velocity, workload, release progress, exports | Future | Pending | Not started |  | BA later | Later phase.
11 | Post-MVP | Portfolio | Initiative/roadmap/cross-project tracking | Future | Pending | Not started |  | BA later | Optional after MVP.

## Progress Tracker
Progress Tracker | Progress Tracker | Progress Tracker | Progress Tracker | Progress Tracker | Progress Tracker | Progress Tracker | Progress Tracker
Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next. | Excel-style tracking sheet: see what is BA done, what Dev has not started, and what is next.
Phase | Slice | BA / Mockup / SRS Status | Production Status | Planned Effort | Dependency | Next Action | Priority
Phase 0 | Foundation | Accepted / historical baseline | Not started | 12 | None | Align with architecture foundation before production. | High
Phase 1 | Manage Projects/Teams/Users | Ready | Not started | 16 | Phase 0 | Dev planning and API/DB review. | High
Phase 1 | Backlog + Create + Detail + Task | Ready | Not started | 16 | Phase 0, Manage | Dev planning and implementation. | High
Phase 1 | Time/Content/Activity | Ready | Not started | 16 | Work Item Detail | Dev planning and implementation. | Medium
Phase 2.1 | Backlog Enhancement | Done | Not started | 9 | Phase 1 Backlog API | Ready for dev after Phase 1. | High
Phase 2.2 | Timeboxes / Iterations | Done | Not started | 14 | Phase 1 Work Item API, Team context | Ready for dev after Phase 2.1 contract. | High
Phase 2.3 | Iteration Status | Done | Not started | 14 | Phase 2.1 + Phase 2.2 | Ready for dev after Iteration and assignment APIs. | High
Phase 3.1 | Team Board | Pending BA confirmation | Not started |  | Phase 2 Iteration Status | Define SRS. | High
Phase 3.2 | Team Status | Pending BA confirmation | Not started |  | Phase 2 Iteration Status | Define SRS. | Medium
Phase 3.3 | Release Management | Pending | Not started |  | Backlog / Iterations | Define SRS. | High
Phase 3.4 | Milestones | Pending | Not started |  | Release / Project planning | Define SRS. | Medium
Phase 3.5 | Quality / Defect | Pending | Not started |  | Work Item foundation | Define SRS. | High
Phase 4 | Collaboration / Governance | Future | Not started |  | Phase 1-3 | Define later. | Medium
Phase 5 | Reporting | Future | Not started |  | Phase 1-4 data | Define later. | Medium
Post-MVP | Portfolio | Future optional | Not started |  | Roadmap decision | Define only if MVP needs it. | Low

## Phase Checklist
Phase Checklist | Phase Checklist | Phase Checklist | Phase Checklist | Phase Checklist
Detailed item status by phase. Use this sheet for BA progress review. | Detailed item status by phase. Use this sheet for BA progress review. | Detailed item status by phase. Use this sheet for BA progress review. | Detailed item status by phase. Use this sheet for BA progress review. | Detailed item status by phase. Use this sheet for BA progress review.
Phase | Item | Status | Owner | Notes
Phase 0 | Login / auth mockup | Done | BA | Login Admin and auth states covered.
Phase 0 | App Shell | Done | BA | Top navigation, breadcrumb, project/team context covered.
Phase 0 | Fixed Company / Workspace | Accepted | BA | Single-company MVP; no Workspace create/switch UI.
Phase 0 | Project list/create/edit/archive mockup | Done | BA | BA accepted fixed company and project creation.
Phase 1 | Backlog base list | Ready | BA | Story/Defect only; Feature/Task not independent backlog items.
Phase 1 | Create Work Item | Ready | BA | Story/Defect quick create and create-with-details defined.
Phase 1 | Work Item Detail | Ready | BA | Details, Tasks, Revision History tabs defined.
Phase 1 | Task Management | Ready | BA | Task is child of Work Item.
Phase 1 | Time Tracking | Ready | BA | Plan Estimate, Estimate, To Do and Actual defined.
Phase 1 | Content / Attachments | Ready | BA | Description, Notes, Attachments, Release Notes defined.
Phase 1 | Activity Log | Ready | BA | Revision History represents basic activity log.
Phase 1 | Manage Projects | Ready | BA | Projects tab kept in Manage.
Phase 1 | Manage Teams | Ready | BA | Team list/create/edit/deactive; member selector in modal.
Phase 1 | Manage Users | Ready | BA | Invite/edit/deactive user; assign user to Team.
Phase 2 | P2.1 Backlog Enhancement | Done | BA | Advanced list behavior and Iteration assignment.
Phase 2 | P2.2 Timeboxes / Iterations | Done | BA | Iteration list/create/detail and assignment options.
Phase 2 | P2.3 Iteration Status | Done | BA | Selector, metrics, list from Backlog assignment, Add Item.
Phase 2 | Project/Team context rule | Done | BA | Workspace selector filters records and defaults create forms.
Phase 2 | Team Board / Team Status | Deferred | BA | Explicitly moved to Phase 3.
Phase 2 | Release Management / Milestones | Deferred | BA | Phase 3 scope.
Phase 3 | Team Board | Pending | BA next | Define create behavior, drag/drop, transitions and WIP.
Phase 3 | Team Status | Pending | BA next | Define KPI/dashboard/list direction.
Phase 3 | Release Management | Pending | BA next | Define release CRUD/readiness/detail.
Phase 3 | Milestones | Pending | BA next | Define delivery checkpoint capability.
Phase 3 | Quality / Defect | Pending | BA next | Define defect lifecycle and quality summary.

## Next Plan
Next Plan | Next Plan | Next Plan | Next Plan | Next Plan | Next Plan
What happens after Phase 2: BA definition first, then dev planning and implementation. | What happens after Phase 2: BA definition first, then dev planning and implementation. | What happens after Phase 2: BA definition first, then dev planning and implementation. | What happens after Phase 2: BA definition first, then dev planning and implementation. | What happens after Phase 2: BA definition first, then dev planning and implementation. | What happens after Phase 2: BA definition first, then dev planning and implementation.
Order | Workstream | Target Output | Dependency | Owner | Status
1 | Confirm Phase 3 scope boundary | Decide exact Phase 3 slices: Team Board/Team Status first, or Release/Quality first. | Phase 2 closure | BA/PO | Next
2 | Define Team Board SRS | Board columns, card fields, create behavior, drag/drop, transition rules, WIP limits, permissions. | Phase 2 Iteration Status | BA | Pending
3 | Define Team Status SRS | KPI list, filters, layout, data source and drill-down behavior. | Phase 2 Iteration Status | BA | Pending
4 | Define Release Management SRS | Release list/detail/create/readiness, included work items, open defects, release status. | Backlog + Iteration assignment | BA | Pending
5 | Define Milestones SRS | Milestone entity, date/owner/status, relationship to release/project/work items. | Release scope | BA | Pending
6 | Define Quality / Defect SRS | Defect lifecycle, severity, environment, steps, verify/reopen, quality summary. | Work Item/Backlog foundation | BA | Pending
7 | Development planning pass | Convert Phase 1 and Phase 2 SRS into sprintable dev tasks with API/DB contract review. | SRS baseline | Tech Lead/Dev Agent | Pending
8 | Production implementation | Implement from foundation through Phase 1 then Phase 2, unless team chooses a vertical slice. | Dev planning | Dev Agent | Pending
Build Order | Capability | Why First | Exit Criteria
1 | Foundation / Phase 0 architecture | Everything depends on auth, routing, company/project/team context and DB migrations. | Login/session, app shell, fixed company, project/team context API ready.
2 | Phase 1 Manage Projects/Teams/Users | Project-Team-User relationships are required by Backlog, Work Item and Iteration context. | Admin can manage Teams/Users; user access derives from Team -> Project.
3 | Phase 1 Backlog + Create | Core work item source of truth must exist before Iteration assignment. | Story/Defect create/list with Project/Team validation.
4 | Phase 1 Work Item Detail + Task | Required for create-with-details, child tasks and later Iteration Status detail drilldown. | Detail/edit/task flows persist data and permissions.
5 | Phase 1 Time/Content/Activity | Adds persistence quality and audit trail. | Estimates, To Do, Actual, attachments and revision history work.
6 | Phase 2.1 Backlog Enhancement | Adds list productivity and Iteration assignment field. | Advanced filters/sort/inline edit/iteration assignment pass tests.
7 | Phase 2.2 Timeboxes / Iterations | Iteration records must exist before Iteration Status. | Create/list/detail Iterations by Project/Team.
8 | Phase 2.3 Iteration Status | Execution visibility over assigned backlog items. | Metrics/list/add item/detail integration work from same source of truth.
9 | Phase 3 Team Board / Team Status | Builds on Iteration Status and Schedule State. | Board/status SRS confirmed and implemented.
10 | Phase 3 Release / Quality / Milestones | Delivery and quality layer on top of work item execution. | Release readiness and defect workflow implemented.

## Risks
Risks & Follow-up | Risks & Follow-up | Risks & Follow-up | Risks & Follow-up | Risks & Follow-up | Risks & Follow-up
Open risks and decision guardrails from the timeline. | Open risks and decision guardrails from the timeline. | Open risks and decision guardrails from the timeline. | Open risks and decision guardrails from the timeline. | Open risks and decision guardrails from the timeline. | Open risks and decision guardrails from the timeline.
ID | Risk / Follow-up | Phase | Impact | Current Handling | Status
TL-R01 | Phase 0 tracking is superseded by newer architecture foundation. | Phase 0 | Medium | Treat Phase 0 old file as historical; use architecture foundation for production. | Open
TL-R02 | Production implementation progress is still 0% in tracking. | All active phases | High | BA docs are ready, but dev planning/implementation must start separately. | Open
TL-R03 | Phase 1 timebox may be tight after adding Manage Teams/Users. | Phase 1 | Medium | Prioritize Create Team and User team membership if scope must split. | Open
TL-R04 | Phase 2 uses UI name Iterations while DB may still call entity sprints. | Phase 2 | Medium | Document alias clearly in API/DB contract before dev. | Open
TL-R05 | Team Board/Team Status mockup exists but is not Phase 2. | Phase 3 | High | Keep Phase 3 placeholder and do not implement during Phase 2. | Decided
TL-R06 | Permission matrix is not fully defined for later phases. | Phase 2+ | Medium | Current mockup assumes Workspace Admin; define roles before production hardening. | Open

## Source Notes
Source Notes | Source Notes
Audit trail for this workbook. | Audit trail for this workbook.
Source | Path
Timeline source | D:/Mini_Rally_pj/Time line.md
Phase 0 checklist | D:/Mini_Rally_pj/04_Developement_tracking/Phase 0/PHASE0_MOCKUP_CHECKLIST.md
Phase 1 checklist | D:/Mini_Rally_pj/04_Developement_tracking/Phase 1/PHASE1_MOCKUP_CHECKLIST.md
Phase 2 checklist | D:/Mini_Rally_pj/04_Developement_tracking/Phase 2/PHASE2_MOCKUP_CHECKLIST.md
Phase 3 placeholder | D:/Mini_Rally_pj/04_Developement_tracking/Phase 3/01_Team_Board_Team_Status/SRS.md
Generation note | This workbook is derived from Time line.md. It is intended as a BA/Dev progress tracker, not a production implementation status report.
Source length | 17958 characters
Generated date | 2026-07-04
File owner | Mini Rally BA tracking